## 1
شرکت مهندسی و طراحی صنایع انرژی ( EIED )
Project Tittle : |  | Basic Engineering Of Khesht oil feild Project Development |  |  | PROGRAM NO.: |  | 1720 |  |  | 1 of 15
[5 empty] | PROJECT NO.: |  | 17202 |  |  | Rev.4
Document Number :
Document Tittle : |  | Document Control Index
Document Control Index
Project Cordinator |  |  | Mahsa Broujerdi |  |  |  | Planning section
Final Issue
[7 empty] | Contractor |  | Client
[7 empty] | Date: |  | Date:
[7 empty] | Sign: |  | Sign:
01 | 2015-05-22 |  | Final Revision | Mahsa Broujerdi |  | Final Issued
Rev. | Date |  | Status | Originator |  | Status |  |  | Approved
THE ORIGINAL AND ALL COPIES OF THIS DOCUMENT TOGETHER WITH THE COPYRIGHT THEREIN ARE THE SOLE PROPERTY OF IRANIAN CENTRAL OIL FIELDS COMPANY.
CHCE Document Number:

## 2
|  |  |  | IRANIAN CENTRAL OIL FIELDS COMPANY (ICOFC) | [7 empty] | CHAGALESH CONSULTING ENGINEERS
Project Tittle : |  |  | Basic Engineering Of Farashband Gas Refinery Development |  |  |  |  | PROGRAM NO.: |  |  | 1720 |  |  | 2 of 15
[8 empty] | PROJECT NO.: |  |  | 17202 |  |  | Rev.4
Document Number :17202B-000-PC-DCI-1001
Document Tittle : |  |  | Document Control Index
| Page | Revisions |  |  |  |  | Remark | Page | Revisions |  |  |  |  | Remark
|  | 0 | 1 | 2 | 3 | 4 |  |  | 0 | 1 | 2 | 3 | 4
| 1 | X
| 2 | X
| 3 | X | X | X | X | X
| 4 | X | X | X | X | X
| 5 | X | X | X | X | X
| 6 | X | X | X | X | X
| 7 | X | X | X | X | X
| 8 | X | X | X | X | X
| 9 | X | X | X | X | X
| 10 |  | X | X | X | X
| 11 |  | X | X | X | X
| 12 |  | X | X | X | X
| 13 |  | X | X |  | X
| 14 |  | X | X |  | X
| 15 |  | X | X |  | X
| 16 |  | X | X
| 17 |  | X | X
| 18 |  | X | X
| 19 |  | X | X
| 20 |  |  | X
| 21 |  |  | X
22
23
24
25
26
27
28
29
4 | FI | Z.Mohammadi |  | K.Khosravi |  | N.Movahedi |  | 89.05.26
3 | FI | Z.Mohammadi |  | K.Khosravi |  | N.Movahedi |  | 89.04.15
2 | IFA | Z.Mohammadi |  | K.Khosravi |  | N.Movahedi |  | 89.02.26
1 | IFA | Z.Mohammadi |  | K.Khosravi |  | N.Movahedi |  | 89.01.14
0 | IFR | Z.Mohammadi |  | K.Khosravi |  | N.Movahedi |  | 88.11.20
REV. | Status | PREPARED |  | CHECKED |  | APPROVED |  | Date |  | CHECKED |  | APPROVED |  | Date
|  | Contractor | [7 empty] | Client
Document Revisions

## DISCIPLINE
ID | DISCIPLINE | ACTIVITY NAME | DOCUMENT TITLE | MAN HOUR | WEIGHT FACTOR | Document No. | Chagalesh Doc. No.
1 | Basic Engineering Of Farashband Gas Refinery Development |  |  | 21999.9959 | 100%
2 | Feasibility Study & Data Gathering |  |  | 5500 | 25%
3 | PROCESS |  | Feasibility Study Report | 5500 | 25% | 17202B-000-PR-RPT-1001 | CH-207-PR-DC-001
4 | Basic Engineering & Hazop Study Of Farashband Gas Refinery Development |  |  | 15399.9959 | 70% | 15400
5 | PROJECT PLANNING & CONTROL |  |  | 470.1976 | 2.137%
6 | PROJECT PLANNING & CONTROL | PC01-DOCUMENTS |  | 240.8777 | 1.095%
7 | PROJECT PLANNING & CONTROL | DOCUMENTS | Document Control Index | 72.3977 | 0.3291% | 17202B-000-PC-DCI-1001 | CH-207-DC-00-001
8 | PROJECT PLANNING & CONTROL | DOCUMENTS | Coordination Procedure | 60.84 | 0.2765% | 17202B-000-PC-CPC-1002 | CH-207-DC-00-002
9 | PROJECT PLANNING & CONTROL | DOCUMENTS | Numbering Procedure | 60.84 | 0.2765% | 17202B-000-PC-NPC-1003 | CH-207-DC-00-003
10 | PROJECT PLANNING & CONTROL | DOCUMENTS | Work Breakdown Structure(WBS) | 46.8 | 0.2127% | 17202B-000-PC-WBS-1004 | CH-207-DC-00-004
11 | PROJECT PLANNING & CONTROL | PC02-PLAN SCHEDULE |  | 229.32 | 1.042%
12 | PROJECT PLANNING & CONTROL | PLAN SCHEDULE | Time Schedule | 229.32 | 1.042% | 17202B-000-PC-SCH-1005 | CH-207-DC-00-005
13 | PROCESS |  |  | 5861.3921 | 26.64%
14 | PROCESS | PR01-DESIGN BASIS |  | 99.8182 | 0.4537%
15 | PROCESS | DESIGN BASIS | Process Design Criteria | 24.9382 | 0.1134% | 17202B-000-PR-DSB-1002 | CH-207-PR-DC-002
16 | PROCESS | DESIGN BASIS | Process Design Basis | 9.36 | 0.04255% | 17202B-000-PR-DSB-1003 | CH-207-PR-DC-003
17 | PROCESS | DESIGN BASIS | Environmental Data | 9.36 | 0.04255% | 17202B-000-PR-EN-1004 | CH-207-PR-DC-004
18 | PROCESS | DESIGN BASIS | Equipment List | 9.36 | 0.04255% | 17202B-000-PR-LST-1005 | CH-207-PR-DC-005
19 | PROCESS | DESIGN BASIS | Line List | 46.8 | 0.2127% | 17202B-000-PR-LST-1096 | CH-207-PR-DC-096
20 | PROCESS | PR02-PROCESS CALCULATION |  | 99.2911 | 0.4513%
21 | PROCESS | PROCESS CALCULATION | Process Simulation Report | 99.2911 | 0.4513% | 17202B-000-PR-RPT-1006 | CH-207-PR-DC-006
22 | PROCESS | PR03-PROCESS FLOW DIAGRAM |  | 104.7182 | 0.476%
23 | PROCESS | PROCESS FLOW DIAGRAM | Block Flow Diagram | 18.72 | 0.08509% | 17202B-000-03-PR-BKD-1097 | CH-207-PR-A3-097
24 | PROCESS | PROCESS FLOW DIAGRAM | Heat and Material Balance Report | 28.08 | 0.1276% | 17202B-000-PR-RPT-1098 | CH-207-PR-098
25 | PROCESS | PROCESS FLOW DIAGRAM | Process Flow Diagrams- Reception Facilities | 14.4795 | 0.06582% | 17202B-100-03-PR-PFD-1007 | CH-207-PR-A3-007
26 | PROCESS | PROCESS FLOW DIAGRAM | Process Flow Diagrams- Gas Dehydration | 14.4795 | 0.06582% | 17202B-200-03-PR-PFD-1008 | CH-207-PR-A3-008
27 | PROCESS | PROCESS FLOW DIAGRAM | Process Flow Diagrams- H/C Dew Point Control | 14.4795 | 0.06582% | 17202B-300-03-PR-PFD-1009 | CH-207-PR-A3-009
28 | PROCESS | PROCESS FLOW DIAGRAM | Process Flow Diagrams- Condensate Stabilization | 14.4795 | 0.06582% | 17202B-400-03-PR-PFD-1010 | CH-207-PR-A3-010
29 | PROCESS | PR04-UTILITY FLOW DIAGRAM |  | 49.8765 | 0.2267%
30 | PROCESS | UTILITY FLOW DIAGRAM | Utility Flow Diagrams- General Utility System | 24.9382 | 0.1134% | 17202B-500-03-PR-UFD-1012 | CH-207-PR-A3-012
31 | PROCESS | UTILITY FLOW DIAGRAM | Utility Flow Diagrams-Air Compression System | 24.9382 | 0.1134% | 17202B-600-03-PR-UFD-1015 | CH-207-PR-A3-015
32 | PROCESS | PR05-MATERIAL SELECTION |  | 161.8274 | 0.7356%
33 | PROCESS | MATERIAL SELECTION | Material Selection Report | 74.3529 | 0.338% | 17202B-000-PR-RPT-1016 | CH-207-PR-DC-016
34 | PROCESS | MATERIAL SELECTION | Material Selection Diagram - Reception Facilities | 14.7782 | 0.06717% | 17202B-100-03-PR-DIG-1017 | CH-207-PR-A3-017
35 | PROCESS | MATERIAL SELECTION | Material Selection Diagram - Gas Dehydration | 14.4795 | 0.06582% | 17202B-200-03-PR-DIG-1020 | CH-207-PR-A3-020
36 | PROCESS | MATERIAL SELECTION | Material Selection Diagram - H/C Dew Point Control | 14.4795 | 0.06582% | 17202B-300-03-PR-DIG-1021 | CH-207-PR-A3-021
37 | PROCESS | MATERIAL SELECTION | Material Selection Diagram - Condensate Stabilization | 14.7782 | 0.06717% | 17202B-400-03-PR-DIG-1058 | CH-207-PR-A3-058
38 | PROCESS | MATERIAL SELECTION | Material Selection Diagram - General Utility System | 14.4795 | 0.06582% | 17202B-500-03-PR-DIG-1018 | CH-207-PR-A3-018
39 | PROCESS | MATERIAL SELECTION | Material Selection Diagram - Air Compression System | 14.4795 | 0.06582% | 17202B-600-03-PR-DIG-1019 | CH-207-PR-A3-019
40 | PROCESS | PR06-DATA SHEET |  | 514.6704 | 2.339%
41 | PROCESS | DATA SHEET | Data Sheet for Pressure vessel - Reception Facilities | 14.4795 | 0.06582% | 17202B-100-PR-DSH-1022 | CH-207-PR-DS-022
42 | PROCESS | DATA SHEET | Data Sheet for filter - Reception Facilities | 14.4795 | 0.06582% | 17202B-100-PR-DSH-1023 | CH-207-PR-DS-023
43 | PROCESS | DATA SHEET | Data Sheet for Safety & Relief Valve - Reception Facilities | 14.4795 | 0.06582% | 17202B-100-PR-DSH-1024 | CH-207-PR-DS-024
44 | PROCESS | DATA SHEET | Data Sheet for Control Valve - Reception Facilities | 14.4795 | 0.06582% | 17202B-100-PR-DSH-1025 | CH-207-PR-DS-025
45 | PROCESS | DATA SHEET | Data Sheet for On/Off valve - Reception Facilities | 14.4795 | 0.06582% | 17202B-100-PR-DSH-1026 | CH-207-PR-DS-026
46 | PROCESS | DATA SHEET | Data Sheet for Pressure vessel - Gas Dehydration | 14.4795 | 0.06582% | 17202B-200-PR-DSH-1027 | CH-207-PR-DS-027
47 | PROCESS | DATA SHEET | Data Sheet for Pump - Gas Dehydration | 14.4795 | 0.06582% | 17202B-200-PR-DSH-1028 | CH-207-PR-DS-028
48 | PROCESS | DATA SHEET | Data Sheet for Heat Exchanger- Gas Dehydration | 14.4795 | 0.06582% | 17202B-200-PR-DSH-1029 | CH-207-PR-DS-029
49 | PROCESS | DATA SHEET | Data Sheet for Air Cooler - Gas Dehydration | 14.4795 | 0.06582% | 17202B-200-PR-DSH-1030 | CH-207-PR-DS-030
50 | PROCESS | DATA SHEET | Data Sheet for filter - Gas Dehydration | 14.4795 | 0.06582% | 17202B-200-PR-DSH-1031 | CH-207-PR-DS-031
51 | PROCESS | DATA SHEET | Data Sheet for Column - Gas Dehydration | 14.4795 | 0.06582% | 17202B-200-PR-DSH-1032 | CH-207-PR-DS-032
52 | PROCESS | DATA SHEET | Data Sheet for Safety & Relief Valve - Gas Dehydration | 14.4795 | 0.06582% | 17202B-200-PR-DSH-1033 | CH-207-PR-DS-033
53 | PROCESS | DATA SHEET | Data Sheet for Control valve - Gas Dehydration | 14.4795 | 0.06582% | 17202B-200-PR-DSH-1034 | CH-207-PR-DS-034
54 | PROCESS | DATA SHEET | Data Sheet for On/Off valve - Gas Dehydration | 14.4795 | 0.06582% | 17202B-200-PR-DSH-1035 | CH-207-PR-DS-035
55 | PROCESS | DATA SHEET | Data Sheet for Pressure vessel - H/C Dew Point Control | 14.4795 | 0.06582% | 17202B-300-PR-DSH-1036 | CH-207-PR-DS-036
56 | PROCESS | DATA SHEET | Data Sheet for Heat Exchanger- H/C Dew Point Control | 14.4795 | 0.06582% | 17202B-300-PR-DSH-1037 | CH-207-PR-DS-037
57 | PROCESS | DATA SHEET | Data Sheet for Safety & Relief Valve - H/C Dew Point Control | 14.4795 | 0.06582% | 17202B-300-PR-DSH-1038 | CH-207-PR-DS-038
58 | PROCESS | DATA SHEET | Data Sheet for Control valve - H/C Dew Point Control | 14.4795 | 0.06582% | 17202B-300-PR-DSH-1039 | CH-207-PR-DS-039
59 | PROCESS | DATA SHEET | Data Sheet for On/Off valve - H/C Dew Point Control | 14.4795 | 0.06582% | 17202B-300-PR-DSH-1040 | CH-207-PR-DS-040
60 | PROCESS | DATA SHEET | Data Sheet for Pressure vessel - Condensate Stabilization | 14.4795 | 0.06582% | 17202B-400-PR-DSH-1041 | CH-207-PR-DS-041
61 | PROCESS | DATA SHEET | Data Sheet for Heat Exchanger- Condensate Stabilization | 14.4795 | 0.06582% | 17202B-400-PR-DSH-1042 | CH-207-PR-DS-042
62 | PROCESS | DATA SHEET | Data Sheet for Air Cooler - Condensate Stabilization | 14.04 | 0.06382% | 17202B-400-PR-DSH-1043 | CH-207-PR-DS-043
63 | PROCESS | DATA SHEET | Data Sheet for Column - Condensate Stabilization | 14.04 | 0.06382% | 17202B-400-PR-DSH-1044 | CH-207-PR-DS-044
64 | PROCESS | DATA SHEET | Data Sheet for Storage Tank -Condensate Stabilization | 14.04 | 0.06382% | 17202B-400-PR-DSH-1045 | CH-207-PR-DS-045
65 | PROCESS | DATA SHEET | Data Sheet for Safety & Relief Valve - Condensate Stabilization | 14.04 | 0.06382% | 17202B-400-PR-DSH-1046 | CH-207-PR-DS-046
66 | PROCESS | DATA SHEET | Data Sheet for Control valve - Condensate Stabilization | 14.04 | 0.06382% | 17202B-400-PR-DSH-1047 | CH-207-PR-DS-047
67 | PROCESS | DATA SHEET | Data Sheet for On/Off valve - Condensate Stabilization | 14.04 | 0.06382% | 17202B-400-PR-DSH-1048 | CH-207-PR-DS-048
68 | PROCESS | DATA SHEET | Data Sheet for Pressure vessel - General Utility System | 14.04 | 0.06382% | 17202B-500-PR-DSH-1049 | CH-207-PR-DS-049
69 | PROCESS | DATA SHEET | Data Sheet for Pump - General Utility System | 14.04 | 0.06382% | 17202B-500-PR-DSH-1050 | CH-207-PR-DS-050
70 | PROCESS | DATA SHEET | Data Sheet for Safety & Relief Valve - General Utility System | 14.04 | 0.06382% | 17202B-500-PR-DSH-1051 | CH-207-PR-DS-051
71 | PROCESS | DATA SHEET | Data Sheet for Control valve - General Utility System | 14.04 | 0.06382% | 17202B-500-PR-DSH-1052 | CH-207-PR-DS-052
72 | PROCESS | DATA SHEET | Data Sheet for Pressure Vessel - Air Compression System | 14.04 | 0.06382% | 17202B-600-PR-DSH-1053 | CH-207-PR-DS-053
73 | PROCESS | DATA SHEET | Data Sheet for Compressor - Air Compression System | 14.04 | 0.06382% | 17202B-600-PR-DSH-1054 | CH-207-PR-DS-054
74 | PROCESS | DATA SHEET | Data Sheet for Dryer - Air Compression System | 14.04 | 0.06382% | 17202B-600-PR-DSH-1055 | CH-207-PR-DS-055
75 | PROCESS | DATA SHEET | Data Sheet for Control Valve - Air Compression System | 14.04 | 0.06382% | 17202B-600-PR-DSH-1056 | CH-207-PR-DS-056
76 | PROCESS | DATA SHEET | Data Sheet for On/Off Valve - Air Compression System | 14.04 | 0.06382% | 17202B-600-PR-DSH-1057 | CH-207-PR-DS-057
77 | PROCESS | PR07-PROCESS SPECIFICATION |  | 48.2651 | 0.2194%
78 | PROCESS | SPECIFICATION | Flare Process Specification | 9.653 | 0.04388% | 17202B-500-PR-SPC-1076 | CH-207-PR-SP-076
79 | PROCESS | SPECIFICATION | Desalter Package Process Specification | 9.653 | 0.04388% | 17202B-400-PR-SPC-1080 | CH-207-PR-SP-080
80 | PROCESS | SPECIFICATION | Hot Oil System Specification | 9.653 | 0.04388% | 17202B-400-PR-SPC-1106 | CH-207-PR-SP-106
81 | PROCESS | SPECIFICATION | Dehydration Package Specification | 9.653 | 0.04388% | 17202B-200-PR-SPC-1107 | CH-207-PR-SP-107
82 | PROCESS | SPECIFICATION | Slug Catcher Process Specification | 9.653 | 0.04388% | 17202B-100-PR-SPC-1108 | CH-207-PR-SP-108
83 | PROCESS | PR08-PIPING & INSTRUMENT DIAGRAM |  | 2299.6006 | 10.45%
84 | PROCESS | PIPING & INSTRUMENT DIAGRAM | Symbol & Legend | 39.5774 | 0.1799% | 17202B-000-03-PR-PID-1081 | CH-207-PR-A3-081
85 | PROCESS | PIPING & INSTRUMENT DIAGRAM | P&ID For Reception Facilities | 160.2403 | 0.7284% | 17202B-100-03-PR-PID-1082 | CH-207-PR-A3-082
86 | PROCESS | PIPING & INSTRUMENT DIAGRAM | P&ID For Reception Facilities (Final Issue) | 162.6202 | 0.7392% | 17202B-100-03-PR-PID-1082 | CH-207-PR-A3-082
87 | PROCESS | PIPING & INSTRUMENT DIAGRAM | P&ID For Gas Dehydration | 160.2403 | 0.7284% | 17202B-200-03-PR-PID-1083 | CH-207-PR-A3-083
88 | PROCESS | PIPING & INSTRUMENT DIAGRAM | P&ID For Gas Dehydration (Final Issue) | 162.6202 | 0.7392% | 17202B-200-03-PR-PID-1083 | CH-207-PR-A3-083
89 | PROCESS | PIPING & INSTRUMENT DIAGRAM | P&ID For H/C Dew Point Control | 160.2403 | 0.7284% | 17202B-300-03-PR-PID-1084 | CH-207-PR-A3-084
90 | PROCESS | PIPING & INSTRUMENT DIAGRAM | P&ID For H/C Dew Point Control (Final Issue) | 162.6202 | 0.7392% | 17202B-300-03-PR-PID-1084 | CH-207-PR-A3-084
91 | PROCESS | PIPING & INSTRUMENT DIAGRAM | P&ID For Condensate Stabilization | 160.2403 | 0.7284% | 17202B-400-03-PR-PID-1085 | CH-207-PR-A3-085
92 | PROCESS | PIPING & INSTRUMENT DIAGRAM | P&ID For Condensate Stabilization (Final Issue) | 162.6202 | 0.7392% | 17202B-400-03-PR-PID-1085 | CH-207-PR-A3-085
93 | PROCESS | PIPING & INSTRUMENT DIAGRAM | P&ID For General Utility System | 160.2403 | 0.7284% | 17202B-500-03-PR-PID-1086 | CH-207-PR-A3-086
94 | PROCESS | PIPING & INSTRUMENT DIAGRAM | P&ID For General Utility System (Final Issue) | 162.6202 | 0.7392% | 17202B-500-03-PR-PID-1086 | CH-207-PR-A3-086
95 | PROCESS | PIPING & INSTRUMENT DIAGRAM | P&ID For Air Compression System | 160.2403 | 0.7284% | 17202B-600-03-PR-PID-1087 | CH-207-PR-A3-087
96 | PROCESS | PIPING & INSTRUMENT DIAGRAM | P&ID For Air Compression System (Final Issue) | 162.6202 | 0.7392% | 17202B-600-03-PR-PID-1087 | CH-207-PR-A3-087
97 | PROCESS | PIPING & INSTRUMENT DIAGRAM | P&ID For Network | 160.2403 | 0.7284% | 17202B-000-03-PR-PID-1088 | CH-207-PR-A3-088
98 | PROCESS | PIPING & INSTRUMENT DIAGRAM | P&ID For Network (Final Issue) | 162.6202 | 0.7392% | 17202B-000-03-PR-PID-1088 | CH-207-PR-A3-088
99 | PROCESS | PR09-SAFE GUARDING PHILOSOPHY |  | 81.4703 | 0.3703%
100 | PROCESS | SAFE GUARDING PHILOSOPHY | ESD Block Diagram | 14.7782 | 0.06717% | 17202B-000-03-PR-BKD-1091 | CH-207-PR-A3-091
101 | PROCESS | SAFE GUARDING PHILOSOPHY | ESD Philosophy | 28.08 | 0.1276% | 17202B-000-PR-DCP-1101 | CH-207-PR-DC-101
102 | PROCESS | SAFE GUARDING PHILOSOPHY | ESD Caus & Effect Diagram | 38.6121 | 0.1755% | 17202B-000-03-PR-DIG-1011 | CH-207-PR-A3-011
103 | PROCESS | PR10-UTILITY / ELECTRICAL POWER CONSUMPTION |  | 44.7513 | 0.2034%
104 | PROCESS | UTILITY / ELECTRICAL POWER CONSUMPTION | Utility & Chemical Consumption Summary | 10.16 | 0.04618% | 17202B-000-PR-LST-1092 | CH-207-PR-DC-092
105 | PROCESS | UTILITY / ELECTRICAL POWER CONSUMPTION | Relief & Load Summary | 24.9382 | 0.1134% | 17202B-000-PR-LST-1093 | CH-207-PR-DC-093
106 | PROCESS | UTILITY / ELECTRICAL POWER CONSUMPTION | Emergency Depressurizing & Minimum Temperature Requirements | 9.653 | 0.04388% | 17202B-000-PR-DCP-1013 | CH-207-PR-DC-013
107 | PROCESS | PR11-OPERATING MANUALS |  | 157.1032 | 0.7141%
108 | PROCESS | OPERATING MANUALS | Process & Utility Description | 26.0632 | 0.1185% | 17202B-000-PR-DCP-1094 | CH-207-PR-DC-094
109 | PROCESS | OPERATING MANUALS | Preliminary Process Description for Safety Systems | 28.08 | 0.1276% | 17202B-000-PR-DCP-1102 | CH-207-PR-DC-102
110 | PROCESS | OPERATING MANUALS | Drainage Philosophy | 28.08 | 0.1276% | 17202B-000-PR-DCP-1103 | CH-207-PR-DC-103
111 | PROCESS | OPERATING MANUALS | Utility Philosophy | 28.08 | 0.1276% | 17202B-000-PR-DCP-1104 | CH-207-PR-DC-104
112 | PROCESS | OPERATING MANUALS | Control Philosophy | 46.8 | 0.2127% | 17202B-000-PR-DCP-1105 | CH-207-PR-DC-105
113 | PROCESS | PR12-HAZOP&HAZID STUDY REPORT |  | 2200 | 10%
114 | PROCESS | HAZOP&HAZID STUDY REPORT | Hazop&Hazid Study Report | 2200 | 10% | 17202B-000-PR-RPT-1095 | CH-207-PR-DC-095
115 | SAFETY |  |  | 566.0239 | 2.573%
116 | SAFETY | SF01-DESIGN BASIS |  | 223.6805 | 1.017%
117 | SAFETY | DESIGN BASIS | Project HSE Requirements | 19.3964 | 0.08817% | 17202B-000-SF-DSB-1001 | CH-207-SA-DC-001
118 | SAFETY | DESIGN BASIS | Safety & Fire Protection Philosophy | 34.632 | 0.1574% | 17202B-000-SF-DCP-1002 | CH-207-SA-DC-002
119 | SAFETY | DESIGN BASIS | Fire Water Demand Calculation | 46.8 | 0.2127% | 17202B-000-SF-CSH-1018 | CH-207-SA-DC-018
120 | SAFETY | DESIGN BASIS | Consequence Analysis | 46.8 | 0.2127% | 17202B-000-SF-RPT-1006 | CH-207-SA-DC-006
121 | SAFETY | DESIGN BASIS | Safety Concept | 37.44 | 0.1702% | 17202B-000-SF-RPT-1020 | CH-207-SA-DC-020
122 | SAFETY | DESIGN BASIS | F&G Design Criteria | 19.3061 | 0.08775% | 17202B-000-SF-DSB-1004 | CH-207-SA-DC-004
123 | SAFETY | DESIGN BASIS | Specification For Hazardous Area Classification | 19.3061 | 0.08775% | 17202B-000-SF-SPC-1007 | CH-207-SA-SP-007
124 | SAFETY | SF02-SAFETY EQUIPMENT |  | 74.0147 | 0.3364%
125 | SAFETY | SAFETY EQUIPMENT | Safety Equipment List | 9.36 | 0.04255% | 17202B-000-SF-LST-1021 | CH-207-SA-DC-021
126 | SAFETY | SAFETY EQUIPMENT | Hazard Source List | 24.9382 | 0.1134% | 17202B-000-SF-LST-1003 | CH-207-SA-DC-003
127 | SAFETY | SAFETY EQUIPMENT | Fire Fighting Equipment Data Sheet | 39.7164 | 0.1805% | 17202B-000-SF-DSH-1005 | CH-207-SA-DS-005
128 | SAFETY | SF03-SAFETY DRAWING |  | 238.3105 | 1.083%
129 | SAFETY | SAFETY DRAWING | Safety Standard Drawings | 14.7782 | 0.06717% | 17202B-000-03-SF-SDG-1008 | CH-207-SA-A3-008
130 | SAFETY | SAFETY DRAWING | F&G Detector Layout For Plant | 24.9382 | 0.1134% | 17202B-000-03-SF-LYT-1009 | CH-207-SA-A3-009
131 | SAFETY | SAFETY DRAWING | F&G Detector Layout For Switchgear Room | 37.5 | 0.1705% | 17202B-900-03-SF-LYT-1010 | CH-207-SA-A3-010
132 | SAFETY | SAFETY DRAWING | F&G Detector Layout For Restaurant | 37.5 | 0.1705% | 17202B-950-03-SF-LYT-1012 | CH-207-SA-A3-012
133 | SAFETY | SAFETY DRAWING | P&ID For Fire Water Network | 44.1407 | 0.2006% | 17202B-000-03-SF-PID-1013 | CH-207-SA-A3-013
134 | SAFETY | SAFETY DRAWING | Safety And Fire Fighting Equipment Layout for plant | 35.3126 | 0.1605% | 17202B-000-03-SF-LYT-1014 | CH-207-SA-A3-014
135 | SAFETY | SAFETY DRAWING | Safety and Firefighting Equipment Layout for Switch Gear Room | 22.0704 | 0.1003% | 17202B-900-03-SF-LYT-1015 | CH-207-SA-A3-015
136 | SAFETY | SAFETY DRAWING | Safety and Firefighting Equipment Layout for Restaurant | 22.0704 | 0.1003% | 17202B-950-03-SF-LYT-1016 | CH-207-SA-A3-016
137 | SAFETY | SF04-PIPING PLAN |  | 30.0182 | 0.1364%
138 | SAFETY | PIPING PLAN | Fire Water Piping Plan | 30.0182 | 0.1364% | 17202B-000-00-SF-PLN-1019 | CH-207-SA-A0-019
139 | MECHANICAL(ROTARY) |  |  | 106.4855 | 0.484%
140 | MECHANICAL(ROTARY) | MM01-DESIGN BASIS |  | 25.4 | 0.1155%
141 | MECHANICAL(ROTARY) | DESIGN BASIS | Mechanical design Criteria | 25.4 | 0.1155% | 17202B-000-ME-DSB-1001 | CH-207-ME-DC-001
142 | MECHANICAL(ROTARY) | MM02-PUMPS |  | 81.0854 | 0.3686%
143 | MECHANICAL(ROTARY) | PUMPS | Mechanical Data Sheet for Pump - Gas Dehydration | 20.2714 | 0.09214% | 17202B-200-ME-DSH-1050 | CH-207-ME-DS-050
144 | MECHANICAL(ROTARY) | PUMPS | Mechanical Data Sheet for Pump - General Utility System | 20.2714 | 0.09214% | 17202B-500-ME-DSH-1051 | CH-207-ME-DS-051
145 | MECHANICAL(ROTARY) | PUMPS | Specification For Centrifugal Pump For Process Service | 20.2714 | 0.09214% | 17202B-000-ME-SPC-1002 | CH-207-ME-SP-002
146 | MECHANICAL(ROTARY) | PUMPS | Material Requisition For Centrifugal Pumps For Process Service | 20.2714 | 0.09214% | 17202B-000-ME-MRQ-1003 | CH-207-ME-DC-003
147 | MECHANICAL(FIX) |  |  | 769.0941 | 3.496%
148 | MECHANICAL(FIX) | EQ01-PRESSURE VESSELS |  | 151.2959 | 0.6877%
149 | MECHANICAL(FIX) | PRESSURE VESSELS | Mechanical Data Sheet for Pressure Vessels - Reception Facilities | 18.9346 | 0.08607% | 17202B-100-ME-DSH-1052 | CH-207-ME-DS-052
150 | MECHANICAL(FIX) | PRESSURE VESSELS | Mechanical Data Sheet for Pressure Vessels - Gas Dehydration | 19.3061 | 0.08775% | 17202B-200-ME-DSH-1053 | CH-207-ME-DS-053
151 | MECHANICAL(FIX) | PRESSURE VESSELS | Mechanical Data Sheet for Pressure Vessels - H/C Dew Point Control | 19.3061 | 0.08775% | 17202B-300-ME-DSH-1054 | CH-207-ME-DS-054
152 | MECHANICAL(FIX) | PRESSURE VESSELS | Mechanical Data Sheet for Pressure Vessels - Condensate Stabilization | 18.9346 | 0.08607% | 17202B-400-ME-DSH-1055 | CH-207-ME-DS-055
153 | MECHANICAL(FIX) | PRESSURE VESSELS | Mechanical Data Sheet for Pressure Vessels - General Utility System | 18.9346 | 0.08607% | 17202B-500-ME-DSH-1056 | CH-207-ME-DS-056
154 | MECHANICAL(FIX) | PRESSURE VESSELS | Mechanical Data Sheet for Pressure Vessel - Air Compression System | 18.9346 | 0.08607% | 17202B-600-ME-DSH-1057 | CH-207-ME-DS-057
155 | MECHANICAL(FIX) | PRESSURE VESSELS | Specification For Pressure Vessel | 18.4728 | 0.08397% | 17202B-000-ME-SPC-1020 | CH-207-ME-SP-020
156 | MECHANICAL(FIX) | PRESSURE VESSELS | Material Requisition For Pressure Vessels | 18.4728 | 0.08397% | 17202B-000-ME-MRQ-1022 | CH-207-ME-DC-022
157 | MECHANICAL(FIX) | EQ02-COLUMNS |  | 89.881 | 0.4086%
158 | MECHANICAL(FIX) | COLUMNS | Mechanical Data Sheet for Column - Gas Dehydration | 17.3755 | 0.07898% | 17202B-200-ME-DSH-1058 | CH-207-ME-DS-058
159 | MECHANICAL(FIX) | COLUMNS | Mechanical Data Sheet for Column - Condensate Stabilization | 17.0873 | 0.07767% | 17202B-400-ME-DSH-1059 | CH-207-ME-DS-059
160 | MECHANICAL(FIX) | COLUMNS | Specification For Column Internal | 18.4728 | 0.08397% | 17202B-000-ME-SPC-1021 | CH-207-ME-SP-021
161 | MECHANICAL(FIX) | COLUMNS | Material Requisition For Columns | 18.4728 | 0.08397% | 17202B-000-ME-MRQ-1023 | CH-207-ME-DC-023
162 | MECHANICAL(FIX) | COLUMNS | Material Requisition For Column Internals | 18.4728 | 0.08397% | 17202B-000-ME-MRQ-1024 | CH-207-ME-DC-024
163 | MECHANICAL(FIX) | EQ03-AIR COOLERS |  | 68.9742 | 0.3135%
164 | MECHANICAL(FIX) | AIR COOLERS | Mechanical Data Sheet for Air Cooler - Gas Dehydration | 14.4795 | 0.06582% | 17202B-200-ME-DSH-1060 | CH-207-ME-DS-060
165 | MECHANICAL(FIX) | AIR COOLERS | Mechanical Data Sheet for Air Cooler - Condensate Stabilization | 14.7782 | 0.06717% | 17202B-400-ME-DSH-1061 | CH-207-ME-DS-061
166 | MECHANICAL(FIX) | AIR COOLERS | Specification For Air Cooler | 19.8582 | 0.09026% | 17202B-000-ME-SPC-1028 | CH-207-ME-SP-028
167 | MECHANICAL(FIX) | AIR COOLERS | Material Requisition For Air Coolers | 19.8582 | 0.09026% | 17202B-000-ME-MRQ-1029 | CH-207-ME-DC-029
168 | MECHANICAL(FIX) | EQ04-HEAT EXCHANGER |  | 83.1551 | 0.378%
169 | MECHANICAL(FIX) | HEAT EXCHANGER | Mechanical Data Sheet for Heat Exchanger- Gas Dehydration | 14.4795 | 0.06582% | 17202B-200-ME-DSH-1062 | CH-207-ME-DS-062
170 | MECHANICAL(FIX) | HEAT EXCHANGER | Mechanical Data Sheet for Heat Exchanger- H/C Dew Point Control | 14.4795 | 0.06582% | 17202B-300-ME-DSH-1063 | CH-207-ME-DS-063
171 | MECHANICAL(FIX) | HEAT EXCHANGER | Mechanical Data Sheet for Heat Exchanger- Condensate Stabilization | 14.4795 | 0.06582% | 17202B-400-ME-DSH-1064 | CH-207-ME-DS-064
172 | MECHANICAL(FIX) | HEAT EXCHANGER | Specification For Shell & Tube Heat Exchanger | 19.8582 | 0.09026% | 17202B-000-ME-SPC-1025 | CH-207-ME-SP-025
173 | MECHANICAL(FIX) | HEAT EXCHANGER | Material Requisition For Shell & Tube Heat Exchangers | 19.8582 | 0.09026% | 17202B-000-ME-MRQ-1026 | CH-207-ME-DC-026
174 | MECHANICAL(FIX) | EQ05-STORAGE TANK |  | 53.2307 | 0.242%
175 | MECHANICAL(FIX) | STORAGE TANK | Mechanical Data Sheet for Storage Tank -Condensate Stabilization | 13.5142 | 0.06143% | 17202B-400-ME-DSH-1065 | CH-207-ME-DS-065
176 | MECHANICAL(FIX) | STORAGE TANK | Specification For Storage Tanks | 19.8582 | 0.09026% | 17202B-000-ME-SPC-1036 | CH-207-ME-SP-036
177 | MECHANICAL(FIX) | STORAGE TANK | Material Requisition For Storage Tanks | 19.8582 | 0.09026% | 17202B-000-ME-MRQ-1037 | CH-207-ME-DC-037
178 | MECHANICAL(FIX) | EQ06-PACKAGES |  | 322.5572 | 1.466%
179 | MECHANICAL(FIX) | PACKAGES | Mechanical Data Sheet for Filter - Reception Facilities | 20.32 | 0.09236% | 17202B-100-ME-DSH-1066 | CH-207-ME-DS-066
180 | MECHANICAL(FIX) | PACKAGES | Mechanical Data Sheet for Filter - Gas Dehydration | 20.2714 | 0.09214% | 17202B-200-ME-DSH-1067 | CH-207-ME-DS-067
181 | MECHANICAL(FIX) | PACKAGES | Mechanical Data Sheet for Compressor - Air Compression System | 20.32 | 0.09236% | 17202B-600-ME-DSH-1068 | CH-207-ME-DS-068
182 | MECHANICAL(FIX) | PACKAGES | Mechanical Data Sheet for Dryer - Air Compression System | 20.32 | 0.09236% | 17202B-600-ME-DSH-1069 | CH-207-ME-DS-069
183 | MECHANICAL(FIX) | PACKAGES | Specification For Filter Package | 43.4386 | 0.1974% | 17202B-000-ME-SPC-1038 | CH-207-ME-SP-038
184 | MECHANICAL(FIX) | PACKAGES | Specification For Instrument Air Compressor & Dryer Package | 43.4386 | 0.1974% | 17202B-600-ME-SPC-1070 | CH-207-ME-SP-070
185 | MECHANICAL(FIX) | PACKAGES | Duty Specification For Condensate Desalter Package | 19.3061 | 0.08775% | 17202B-400-ME-SPC-1042 | CH-207-ME-SP-042
186 | MECHANICAL(FIX) | PACKAGES | Duty Specification For Hot Oil System | 19.3061 | 0.08775% | 17202B-400-ME-SPC-1077 | CH-207-ME-SP-077
187 | MECHANICAL(FIX) | PACKAGES | Duty Specification For Flare Package | 19.3061 | 0.08775% | 17202B-500-ME-SPC-1044 | CH-207-ME-SP-044
188 | MECHANICAL(FIX) | PACKAGES | Duty Specification For Gas Dehydration | 19.3061 | 0.08775% | 17202B-200-ME-SPC-1078 | CH-207-ME-SP-078
189 | MECHANICAL(FIX) | PACKAGES | Material Requisition For Filter Package | 19.3061 | 0.08775% | 17202B-000-ME-MRQ-1039 | CH-207-ME-DC-039
190 | MECHANICAL(FIX) | PACKAGES | Material Requisition For Condensate Desalter Package | 19.3061 | 0.08775% | 17202B-400-ME-MRQ-1043 | CH-207-ME-DC-043
191 | MECHANICAL(FIX) | PACKAGES | Material Requisition For Flare Package | 19.3061 | 0.08775% | 17202B-500-ME-MRQ-1045 | CH-207-ME-DC-045
192 | MECHANICAL(FIX) | PACKAGES | Material Requisition For Instrument Air Compressor & Dryer Package | 19.3061 | 0.08775% | 17202B-800-ME-MRQ-1046 | CH-207-ME-DC-046
193 | MECHANICAL(HVAC) |  |  | 445.6553 | 2.026%
194 | MECHANICAL(HVAC) | HV01-DESIGN BASIS |  | 25.4 | 0.1155%
195 | MECHANICAL(HVAC) | DESIGN BASIS | HVAC & Plumbing Design Basis | 25.4 | 0.1155% | 17202B-000-HV-DSB-1084 | CH-207-HV-DC-084
196 | MECHANICAL(HVAC) | HV02-HVAC EQUIPMENT |  | 85.8983 | 0.3904%
197 | MECHANICAL(HVAC) | HVAC EQUIPMENT | HVAC Data sheet for Substation | 23.5528 | 0.1071% | 17202B-900-HV-DSH-1087 | CH-207-HV-DS-087
198 | MECHANICAL(HVAC) | HVAC EQUIPMENT | HVAC Data sheet for Restaurant | 22.1673 | 0.1008% | 17202B-950-HV-DSH-1089 | CH-207-HV-DS-089
199 | MECHANICAL(HVAC) | HVAC EQUIPMENT | Specification For HVAC | 7.8509 | 0.03569% | 17202B-000-HV-SPC-1085 | CH-207-HV-SP-085
200 | MECHANICAL(HVAC) | HVAC EQUIPMENT | Material Requisition for HVAC Main Equipment | 18.4728 | 0.08397% | 17202B-000-HV-MRQ-1111 | CH-207-HV-DC-111
201 | MECHANICAL(HVAC) | HVAC EQUIPMENT | Material Requisition for HVAC Accessories | 13.8546 | 0.06298% | 17202B-000-HV-MRQ-1112 | CH-207-HV-DC-112
202 | MECHANICAL(HVAC) | HV03-HVAC DRAWING |  | 238.7604 | 1.085%
203 | MECHANICAL(HVAC) | HVAC DRAWING | Legend and abbreviation for HVAC | 14.7782 | 0.06717% | 17202B-000-02-HV-DIG-1093 | CH-207-HV-A2-093
204 | MECHANICAL(HVAC) | HVAC DRAWING | Typical Details for HVAC System-1 | 9.2364 | 0.04198% | 17202B-000-02-HV-DDG-1094 | CH-207-HV-A2-094
205 | MECHANICAL(HVAC) | HVAC DRAWING | Typical Details for HVAC System-2 | 9.2364 | 0.04198% | 17202B-000-02-HV-DDG-1095 | CH-207-HV-A2-095
206 | MECHANICAL(HVAC) | HVAC DRAWING | Typical Details for HVAC System-3 | 9.2364 | 0.04198% | 17202B-000-02-HV-DDG-1096 | CH-207-HV-A2-096
207 | MECHANICAL(HVAC) | HVAC DRAWING | Typical Details for HVAC System-4 | 9.2364 | 0.04198% | 17202B-000-02-HV-DDG-1097 | CH-207-HV-A2-097
208 | MECHANICAL(HVAC) | HVAC DRAWING | Air Flow & Control Diagram For Substation | 51.9546 | 0.2362% | 17202B-900-02-HV-DIG-1088 | CH-207-HV-A2-088
209 | MECHANICAL(HVAC) | HVAC DRAWING | Air Flow And Control Diagram For Restaurant | 51.9546 | 0.2362% | 17202B-950-HV-DIG-1090 | CH-207-HV-DC-090
210 | MECHANICAL(HVAC) | HVAC DRAWING | HVAC System-1 for Restaurant | 11.5455 | 0.05248% | 17202B-950-02-HV-DDG-1101 | CH-207-HV-A2-101
211 | MECHANICAL(HVAC) | HVAC DRAWING | HVAC System-2 for Restaurant | 11.5455 | 0.05248% | 17202B-950-02-HV-DDG-1102 | CH-207-HV-A2-102
212 | MECHANICAL(HVAC) | HVAC DRAWING | HVAC Room enlarged plan for Restaurant | 36.9455 | 0.1679% | 17202B-950-02-HV-DDG-1103 | CH-207-HV-A2-103
213 | MECHANICAL(HVAC) | HVAC DRAWING | Roof HVAC plan for Restaurant | 23.0909 | 0.105% | 17202B-950-02-HV-DDG-1104 | CH-207-HV-A2-104
214 | MECHANICAL(HVAC) | HV04-PLUMBING SYSTEM |  | 95.5965 | 0.4345%
215 | MECHANICAL(HVAC) | PLUMBING SYSTEM | Specification For Plumbing | 7.8509 | 0.03569% | 17202B-000-HV-SPC-1086 | CH-207-HV-SP-086
216 | MECHANICAL(HVAC) | PLUMBING SYSTEM | Typical Details for Plumbing System-1 | 9.2364 | 0.04198% | 17202B-000-02-HV-DDG-1098 | CH-207-HV-A2-098
217 | MECHANICAL(HVAC) | PLUMBING SYSTEM | Typical Details for Plumbing System-2 | 9.2364 | 0.04198% | 17202B-000-02-HV-DDG-1099 | CH-207-HV-A2-099
218 | MECHANICAL(HVAC) | PLUMBING SYSTEM | Typical Details for Plumbing System-3 | 9.2364 | 0.04198% | 17202B-000-02-HV-DDG-1100 | CH-207-HV-A2-100
219 | MECHANICAL(HVAC) | PLUMBING SYSTEM | Plumbing Plan-1 for Restaurant | 23.0909 | 0.105% | 17202B-950-02-HV-DDG-1107 | CH-207-HV-A2-107
220 | MECHANICAL(HVAC) | PLUMBING SYSTEM | Plumbing Plan-2 for Restaurant | 23.0909 | 0.105% | 17202B-950-02-HV-DDG-1108 | CH-207-HV-A2-108
221 | MECHANICAL(HVAC) | PLUMBING SYSTEM | Material Requisition for Plumbing Accessories | 13.8546 | 0.06298% | 17202B-000-HV-MRQ-1113 | CH-207-HV-DC-113
222 | CIVIL |  |  | 1719.3521 | 7.815%
223 | CIVIL | CI01-DESIGN BASIS |  | 30.0182 | 0.1364%
224 | CIVIL | DESIGN BASIS | Civil Design Basis | 30.0182 | 0.1364% | 17202B-000-CV-DSB-1001 | CH-207-CI-SP-001
225 | CIVIL | CI02-SPECIFICATION |  | 158.8657 | 0.7221%
226 | CIVIL | SPECIFICATION | Specification For Steel Work | 19.8582 | 0.09026% | 17202B-000-ST-SPC-1002 | CH-207-ST-SP-002
227 | CIVIL | SPECIFICATION | Specification For Concrete Work | 19.8582 | 0.09026% | 17202B-000-ST-SPC-1003 | CH-207-ST-SP-003
228 | CIVIL | SPECIFICATION | Specification For Grouting | 19.8582 | 0.09026% | 17202B-000-ST-SPC-1004 | CH-207-ST-SP-004
229 | CIVIL | SPECIFICATION | Specification For Fencing | 19.8582 | 0.09026% | 17202B-000-CV-SPC-1067 | CH-207-CI-SP-067
230 | CIVIL | SPECIFICATION | Specification For Fire Proofing | 19.8582 | 0.09026% | 17202B-000-ST-SPC-1068 | CH-207-ST-SP-068
231 | CIVIL | SPECIFICATION | Specification For Road & Paving | 19.8582 | 0.09026% | 17202B-000-CV-SPC-1005 | CH-207-CI-SP-005
232 | CIVIL | SPECIFICATION | Specification For Sewer & Drainage | 19.8582 | 0.09026% | 17202B-000-CV-SPC-1006 | CH-207-CI-SP-006
233 | CIVIL | SPECIFICATION | Specification For Earth Work | 19.8582 | 0.09026% | 17202B-000-CV-SPC-1007 | CH-207-CI-SP-007
234 | CIVIL | CI03-ARCHITECTURAL WORKS |  | 595.7465 | 2.708%
235 | CIVIL | ARCHITECTURAL WORKS | Restaurant Building Plan | 76.2001 | 0.3464% | 17202B-950-01-BL-DDG-1008 | CH-207-AR-A1-008
236 | CIVIL | ARCHITECTURAL WORKS | Restaurant Building Roof Plan | 76.2001 | 0.3464% | 17202B-950-01-BL-DDG-1009 | CH-207-AR-A1-009
237 | CIVIL | ARCHITECTURAL WORKS | Restaurant Building Elevation | 76.2001 | 0.3464% | 17202B-950-01-BL-DDG-1010 | CH-207-AR-A1-010
238 | CIVIL | ARCHITECTURAL WORKS | Restaurant Building Wall Section & Details | 76.2001 | 0.3464% | 17202B-950-01-BL-DDG-1011 | CH-207-AR-A1-011
239 | CIVIL | ARCHITECTURAL WORKS | Restaurant Building Door & Finishing Schedule | 76.2001 | 0.3464% | 17202B-950-01-BL-DDG-1012 | CH-207-AR-A1-012
240 | CIVIL | ARCHITECTURAL WORKS | Substation Building Plan | 76.2001 | 0.3464% | 17202B-900-01-BL-DDG-1018 | CH-207-AR-A1-018
241 | CIVIL | ARCHITECTURAL WORKS | Substation Building Elevation | 76.2001 | 0.3464% | 17202B-900-01-BL-DDG-1019 | CH-207-AR-A1-019
242 | CIVIL | ARCHITECTURAL WORKS | Substation Building Finishing Schedule & Detail | 62.3456 | 0.2834% | 17202B-900-01-BL-DDG-1020 | CH-207-AR-A1-020
243 | CIVIL | CI04-STEEL STRUCTURE |  | 200.8913 | 0.9131%
244 | CIVIL | STEEL STRUCTURE | Restaurant Building Section & Details | 76.2001 | 0.3464% | 17202B-950-01-ST-DDG-1021 | CH-207-ST-A1-021
245 | CIVIL | STEEL STRUCTURE | Restaurant Building Framing Plan & Elevation | 62.3456 | 0.2834% | 17202B-950-01-ST-DDG-1022 | CH-207-ST-A1-022
246 | CIVIL | STEEL STRUCTURE | Restaurant Building Structural Details | 62.3456 | 0.2834% | 17202B-950-01-ST-DDG-1023 | CH-207-ST-A1-023
247 | CIVIL | CI05-CONCRETE STRUCTURE |  | 119.1493 | 0.5416%
248 | CIVIL | CONCRETE STRUCTURE | Foundation for Restaurant Building Formwork & Reinforcement | 59.5747 | 0.2708% | 17202B-950-01-ST-DDG-1027 | CH-207-ST-A1-027
249 | CIVIL | CONCRETE STRUCTURE | Foundation for Restaurant Building Bars Bending Schedule | 59.5747 | 0.2708% | 17202B-950-04-ST-SCH-1028 | CH-207-ST-A4-028
250 | CIVIL | CI06-CIVIL WORK |  | 333.8951 | 1.518%
251 | CIVIL | CIVIL WORK | Civil Arrangement Layout | 49.8765 | 0.2267% | 17202B-000-01-CV-LYT-1031 | CH-207-CI-A1-031
252 | CIVIL | CIVIL WORK | Civil Layout For Restaurant Area | 74.8147 | 0.3401% | 17202B-950-01-CV-LYT-1032 | CH-207-CI-A1-032
253 | CIVIL | CIVIL WORK | Rough Grading Layout | 74.8147 | 0.3401% | 17202B-000-01-CV-DWG-1033 | CH-207-CI-A1-033
254 | CIVIL | CIVIL WORK | Preliminary Drainage & Grading Layout | 59.5747 | 0.2708% | 17202B-000-01-CV-LYT-1034 | CH-207-CI-A1-034
255 | CIVIL | CIVIL WORK | Sanitary Layout For Restaurant Area | 74.8147 | 0.3401% | 17202B-950-01-CV-LYT-1035 | CH-207-CI-A1-035
256 | CIVIL | CI07-CIVIL & STRUCTURE STANDARD DRAWING |  | 280.7859 | 1.276%
257 | CIVIL | CIVIL & STRUCTURE STANDARD DRAWING | Civil Standard Drawing - Road & Paving Detail | 14.7782 | 0.06717% | 17202B-000-03-CV-SDG-1036 | CH-207-CI-A3-036
258 | CIVIL | CIVIL & STRUCTURE STANDARD DRAWING | Civil Standard Drawing - Road Section & Detail | 14.7782 | 0.06717% | 17202B-000-03-CV-SDG-1037 | CH-207-CI-A3-037
259 | CIVIL | CIVIL & STRUCTURE STANDARD DRAWING | Civil Standard Drawing - Cable Trench Detail | 14.7782 | 0.06717% | 17202B-000-03-CV-SDG-1039 | CH-207-CI-A3-039
260 | CIVIL | CIVIL & STRUCTURE STANDARD DRAWING | Civil Standard Drawing - Road Crossing Conduits For Elec. Or Instrument cables | 14.7782 | 0.06717% | 17202B-000-03-CV-SDG-1040 | CH-207-CI-A3-040
261 | CIVIL | CIVIL & STRUCTURE STANDARD DRAWING | Civil Standard Drawing - Conduits Under Pipe Ways For Elec. Or Instrument Cables | 14.7782 | 0.06717% | 17202B-000-03-CV-SDG-1041 | CH-207-CI-A3-041
262 | CIVIL | CIVIL & STRUCTURE STANDARD DRAWING | Civil Standard Drawing - Submerged Pipe To Manhole | 14.7782 | 0.06717% | 17202B-000-03-CV-SDG-1042 | CH-207-CI-A3-042
263 | CIVIL | CIVIL & STRUCTURE STANDARD DRAWING | Civil Standard Drawing - Oily Water System Manhole Details | 14.7782 | 0.06717% | 17202B-000-03-CV-SDG-1043 | CH-207-CI-A3-043
264 | CIVIL | CIVIL & STRUCTURE STANDARD DRAWING | Civil Standard Drawing - Oily Water Manhole Double Compartment Manhole (Dia > 20") | 14.7782 | 0.06717% | 17202B-000-03-CV-SDG-1044 | CH-207-CI-A3-044
265 | CIVIL | CIVIL & STRUCTURE STANDARD DRAWING | Civil Standard Drawing - U/G Oily Sewer Clean Out | 14.7782 | 0.06717% | 17202B-000-03-CV-SDG-1045 | CH-207-CI-A3-045
266 | CIVIL | CIVIL & STRUCTURE STANDARD DRAWING | Civil Standard Drawing - Sanitary Manhole Details | 14.7782 | 0.06717% | 17202B-000-03-CV-SDG-1046 | CH-207-CI-A3-046
267 | CIVIL | CIVIL & STRUCTURE STANDARD DRAWING | Civil Standard Drawing - Oily Water Manhole Vent Detail | 14.7782 | 0.06717% | 17202B-000-03-CV-SDG-1047 | CH-207-CI-A3-047
268 | CIVIL | CIVIL & STRUCTURE STANDARD DRAWING | Civil Standard Drawing - Fence and gate Details | 14.7782 | 0.06717% | 17202B-000-03-CV-SDG-1048 | CH-207-CI-A3-048
269 | CIVIL | CIVIL & STRUCTURE STANDARD DRAWING | Civil Standard Drawing - Greese trap detail | 14.7782 | 0.06717% | 17202B-000-03-CV-SDG-1049 | CH-207-CI-A3-049
270 | CIVIL | CIVIL & STRUCTURE STANDARD DRAWING | Structural Standard Drawing - Anchor Bolts | 14.7782 | 0.06717% | 17202B-000-01-ST-SDG-1050 | CH-207-ST-A1-050
271 | CIVIL | CIVIL & STRUCTURE STANDARD DRAWING | Structural Standard Drawing - Ladder Detail | 14.7782 | 0.06717% | 17202B-000-03-ST-SDG-1051 | CH-207-ST-A3-051
272 | CIVIL | CIVIL & STRUCTURE STANDARD DRAWING | Structural Standard Drawing - Stair Detail | 14.7782 | 0.06717% | 17202B-000-03-ST-SDG-1052 | CH-207-ST-A3-052
273 | CIVIL | CIVIL & STRUCTURE STANDARD DRAWING | Structural Standard Drawing - Handrail | 14.7782 | 0.06717% | 17202B-000-03-ST-SDG-1053 | CH-207-ST-A3-053
274 | CIVIL | CIVIL & STRUCTURE STANDARD DRAWING | Structural Standard Drawing - Fire Proofing Detail | 14.7782 | 0.06717% | 17202B-000-03-ST-SDG-1054 | CH-207-ST-A3-054
275 | CIVIL | CIVIL & STRUCTURE STANDARD DRAWING | Structural Standard Drawing - Lighting Pole Foundation | 14.7782 | 0.06717% | 17202B-000-03-ST-SDG-1055 | CH-207-ST-A3-055
276 | INSTRUMENT |  |  | 3221.7314 | 14.64%
277 | INSTRUMENT | IN01-DESIGN BASIS |  | 49.8765 | 0.2267%
278 | INSTRUMENT | DESIGN BASIS | Instrument Design Criteria | 49.8765 | 0.2267% | 17202B-000-IN-DSB-1001 | CH-207-IN-DC-001
279 | INSTRUMENT | IN02-SUPERVISION & CONTROL SYSTEM |  | 75.7383 | 0.3443%
280 | INSTRUMENT | SUPERVISION & CONTROL SYSTEM | Specification For Control System (DCS) | 30.0182 | 0.1364% | 17202B-000-IN-SPC-1002 | CH-207-IN-SP-002
281 | INSTRUMENT | SUPERVISION & CONTROL SYSTEM | I/O List For DCS | 33.251 | 0.1511% | 17202B-000-IN-SGL-1003 | CH-207-IN-DC-003
282 | INSTRUMENT | SUPERVISION & CONTROL SYSTEM | Control System Block Diagram Configuration | 12.4691 | 0.05668% | 17202B-000-03-IN-SCD-1004 | CH-207-IN-A3-004
283 | INSTRUMENT | IN03-ESD & F&G CONFIGURATION |  | 124.2112 | 0.5646%
284 | INSTRUMENT | ESD & F&G CONFIGURATION | Specification For Emergency Shutdown System (ESD) | 30.0182 | 0.1364% | 17202B-000-IN-SPC-1005 | CH-207-IN-SP-005
285 | INSTRUMENT | ESD & F&G CONFIGURATION | I/O List For ESD | 32.3273 | 0.1469% | 17202B-000-IN-SGL-1006 | CH-207-IN-DC-006
286 | INSTRUMENT | ESD & F&G CONFIGURATION | Specification For Fire & Gas System (F&G) | 28.08 | 0.1276% | 17202B-000-IN-SPC-1007 | CH-207-IN-SP-007
287 | INSTRUMENT | ESD & F&G CONFIGURATION | F&G Layout For Area | 14.4795 | 0.06582% | 17202B-000-00-IN-LYT-1015 | CH-207-IN-A0-015
288 | INSTRUMENT | ESD & F&G CONFIGURATION | F&G Layout For Substation Building | 9.653 | 0.04388% | 17202B-900-01-IN-LYT-1016 | CH-207-IN-A1-016
289 | INSTRUMENT | ESD & F&G CONFIGURATION | F&G Layout For Restaurant Building | 9.653 | 0.04388% | 17202B-950-01-IN-LYT-1017 | CH-207-IN-A1-017
290 | INSTRUMENT | IN04-INSTRUMENT VALVES |  | 881.7053 | 4.008%
291 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Control Valves For Unit 100 | 4.68 | 0.02127% | 17202B-100-IN-DSH-1033 | CH-207-IN-DS-033
292 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Control Valves For Unit 100 (Final Issue) | 26.2495 | 0.1193% | 17202B-100-IN-DSH-1033 | CH-207-IN-DS-033
293 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Control Valves For Unit 200 | 4.8265 | 0.02194% | 17202B-200-IN-DSH-1034 | CH-207-IN-DS-034
294 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Control Valves For Unit 200 (Final Issue) | 26.7603 | 0.1216% | 17202B-200-IN-DSH-1034 | CH-207-IN-DS-034
295 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Control Valves For Unit 300 | 4.68 | 0.02127% | 17202B-300-IN-DSH-1035 | CH-207-IN-DS-035
296 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Control Valves For Unit 300 (Final Issue) | 26.2495 | 0.1193% | 17202B-300-IN-DSH-1035 | CH-207-IN-DS-035
297 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Control Valves For Unit 400 | 4.68 | 0.02127% | 17202B-400-IN-DSH-1036 | CH-207-IN-DS-036
298 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Control Valves For Unit 400 (Final Issue) | 26.2495 | 0.1193% | 17202B-400-IN-DSH-1036 | CH-207-IN-DS-036
299 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Control Valves For Unit 500 | 4.68 | 0.02127% | 17202B-500-IN-DSH-1037 | CH-207-IN-DS-037
300 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Control Valves For Unit 500 (Final Issue) | 26.2495 | 0.1193% | 17202B-500-IN-DSH-1037 | CH-207-IN-DS-037
301 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Control Valves For Unit 600 | 4.8265 | 0.02194% | 17202B-600-IN-DSH-1038 | CH-207-IN-DS-038
302 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Control Valves For Unit 600 (Final Issue) | 26.7603 | 0.1216% | 17202B-600-IN-DSH-1038 | CH-207-IN-DS-038
303 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Pressure Safety Valves For Unit 100 | 4.68 | 0.02127% | 17202B-100-IN-DSH-1039 | CH-207-IN-DS-039
304 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Pressure Safety ValvesFor Unit 100 (Final Issue) | 26.2495 | 0.1193% | 17202B-100-IN-DSH-1039 | CH-207-IN-DS-039
305 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Pressure Safety Valves For Unit 200 | 4.8265 | 0.02194% | 17202B-200-IN-DSH-1040 | CH-207-IN-DS-040
306 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Pressure Safety ValvesFor Unit 200 (Final Issue) | 26.7603 | 0.1216% | 17202B-200-IN-DSH-1040 | CH-207-IN-DS-040
307 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Pressure Safety Valves For Unit 300 | 4.68 | 0.02127% | 17202B-300-IN-DSH-1041 | CH-207-IN-DS-041
308 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Pressure Safety Valves For Unit 300 (Final Issue) | 26.2495 | 0.1193% | 17202B-300-IN-DSH-1041 | CH-207-IN-DS-041
309 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Pressure Safety Valves For Unit 400 | 4.68 | 0.02127% | 17202B-400-IN-DSH-1042 | CH-207-IN-DS-042
310 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Pressure Safety Valves For Unit 400 (Final Issue) | 26.2495 | 0.1193% | 17202B-400-IN-DSH-1042 | CH-207-IN-DS-042
311 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Pressure Safety Valves For Unit 500 | 4.68 | 0.02127% | 17202B-500-IN-DSH-1043 | CH-207-IN-DS-043
312 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Pressure Safety Valves For Unit 500 (Final Issue) | 26.2495 | 0.1193% | 17202B-500-IN-DSH-1043 | CH-207-IN-DS-043
313 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Pressure Safety Valves For Unit 600 | 4.8265 | 0.02194% | 17202B-600-IN-DSH-1044 | CH-207-IN-DS-044
314 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Pressure Safety Valves For Unit 600 (Final Issue) | 26.7603 | 0.1216% | 17202B-600-IN-DSH-1044 | CH-207-IN-DS-044
315 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For On/Off Valves For Unit 100 | 4.68 | 0.02127% | 17202B-100-IN-DSH-1045 | CH-207-IN-DS-045
316 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For On/Off Valves For Unit 100(Final Issue) | 26.2495 | 0.1193% | 17202B-100-IN-DSH-1045 | CH-207-IN-DS-045
317 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For On/Off Valves For Unit 200 | 4.8265 | 0.02194% | 17202B-200-IN-DSH-1046 | CH-207-IN-DS-046
318 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For On/Off Valves For Unit 200(Final Issue) | 26.7603 | 0.1216% | 17202B-200-IN-DSH-1046 | CH-207-IN-DS-046
319 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For On/Off Valves For Unit 300 | 4.68 | 0.02127% | 17202B-300-IN-DSH-1047 | CH-207-IN-DS-047
320 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For On/Off Valves For Unit 300(Final Issue) | 26.2495 | 0.1193% | 17202B-300-IN-DSH-1047 | CH-207-IN-DS-047
321 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For On/Off Valves For Unit 400 | 4.68 | 0.02127% | 17202B-400-IN-DSH-1048 | CH-207-IN-DS-048
322 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For On/Off Valves For Unit 400(Final Issue) | 26.2495 | 0.1193% | 17202B-400-IN-DSH-1048 | CH-207-IN-DS-048
323 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For On/Off Valves For Unit 500 | 4.68 | 0.02127% | 17202B-500-IN-DSH-1049 | CH-207-IN-DS-049
324 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For On/Off Valves For Unit 500(Final Issue) | 26.2495 | 0.1193% | 17202B-500-IN-DSH-1049 | CH-207-IN-DS-049
325 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For On/Off Valves For Unit 600 | 4.8265 | 0.02194% | 17202B-600-IN-DSH-1050 | CH-207-IN-DS-050
326 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For On/Off Valves For Unit 600(Final Issue) | 26.7603 | 0.1216% | 17202B-600-IN-DSH-1050 | CH-207-IN-DS-050
327 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Motor Operated Valves For Unit 100 | 4.68 | 0.02127% | 17202B-100-IN-DSH-1051 | CH-207-IN-DS-051
328 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Motor Operated Valves For Unit 100(Final Issue) | 26.2495 | 0.1193% | 17202B-100-IN-DSH-1051 | CH-207-IN-DS-051
329 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Motor Operated Valves For Unit 200 | 4.8265 | 0.02194% | 17202B-200-IN-DSH-1052 | CH-207-IN-DS-052
330 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Motor Operated Valves For Unit 200(Final Issue) | 26.7603 | 0.1216% | 17202B-200-IN-DSH-1052 | CH-207-IN-DS-052
331 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Motor Operated Valves For Unit 300 | 4.68 | 0.02127% | 17202B-300-IN-DSH-1053 | CH-207-IN-DS-053
332 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Motor Operated Valves For Unit 300(Final Issue) | 24.1857 | 0.1099% | 17202B-300-IN-DSH-1053 | CH-207-IN-DS-053
333 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Motor Operated Valves For Unit 400 | 4.68 | 0.02127% | 17202B-400-IN-DSH-1054 | CH-207-IN-DS-054
334 | INSTRUMENT | INSTRUMENT VALVES | Data Sheet For Motor Operated Valves For Unit 400(Final Issue) | 24.1857 | 0.1099% | 17202B-400-IN-DSH-1054 | CH-207-IN-DS-054
335 | INSTRUMENT | INSTRUMENT VALVES | Instrument Specification For Control Valves | 50.1957 | 0.2282% | 17202B-000-IN-SPC-1008 | CH-207-IN-SP-008
336 | INSTRUMENT | INSTRUMENT VALVES | Instrument Specification For On-Off Valves | 50.1957 | 0.2282% | 17202B-000-IN-SPC-1009 | CH-207-IN-SP-009
337 | INSTRUMENT | INSTRUMENT VALVES | Instrument Specification For Motor Operated Valves | 50.1957 | 0.2282% | 17202B-000-IN-SPC-1010 | CH-207-IN-SP-010
338 | INSTRUMENT | INSTRUMENT VALVES | Instrument Specification For Pressure Safety Valves | 50.1957 | 0.2282% | 17202B-000-IN-SPC-1011 | CH-207-IN-SP-011
339 | INSTRUMENT | IN05-MEASURMENT & CONTROL INSTRUMENT |  | 1956.9401 | 8.895%
340 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | General Specification For Instrumentation | 62.3456 | 0.2834% | 17202B-000-IN-SPC-1012 | CH-207-IN-SP-012
341 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Instrument Specification For Package Units | 28.6328 | 0.1301% | 17202B-000-IN-SPC-1013 | CH-207-IN-SP-013
342 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Specification For Corrosion Instruments | 28.6328 | 0.1301% | 17202B-000-IN-SPC-1014 | CH-207-IN-SP-014
343 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Instrument List For Unit 100 | 4.68 | 0.02127% | 17202B-100-IN-INX-1069 | CH-207-IN-DC-069
344 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Instrument List For Unit 100(Final Issue) | 26.2495 | 0.1193% | 17202B-100-IN-INX-1069 | CH-207-IN-DC-069
345 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Instrument List For Unit 200 | 4.8265 | 0.02194% | 17202B-200-IN-INX-1070 | CH-207-IN-DC-070
346 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Instrument List For Unit 200(Final Issue) | 26.7603 | 0.1216% | 17202B-200-IN-INX-1070 | CH-207-IN-DC-070
347 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Instrument List For Unit 300 | 4.68 | 0.02127% | 17202B-300-IN-INX-1071 | CH-207-IN-DC-071
348 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Instrument List For Unit 300(Final Issue) | 26.2495 | 0.1193% | 17202B-300-IN-INX-1071 | CH-207-IN-DC-071
349 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Instrument List For Unit 400 | 4.68 | 0.02127% | 17202B-400-IN-INX-1072 | CH-207-IN-DC-072
350 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Instrument List For Unit 400(Final Issue) | 26.2495 | 0.1193% | 17202B-400-IN-INX-1072 | CH-207-IN-DC-072
351 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Instrument List For Unit 500 | 4.68 | 0.02127% | 17202B-500-IN-INX-1073 | CH-207-IN-DC-073
352 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Instrument List For Unit 500(Final Issue) | 26.2495 | 0.1193% | 17202B-500-IN-INX-1073 | CH-207-IN-DC-073
353 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Instrument List For Unit 600 | 4.8265 | 0.02194% | 17202B-600-IN-INX-1074 | CH-207-IN-DC-074
354 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Instrument List For Unit 600(Final Issue) | 26.7603 | 0.1216% | 17202B-600-IN-INX-1074 | CH-207-IN-DC-074
355 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Flow Elements For Unit 100 | 4.68 | 0.02127% | 17202B-100-IN-DSH-1075 | CH-207-IN-DS-075
356 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Flow Elements For Unit 100(Final Issue) | 26.2495 | 0.1193% | 17202B-100-IN-DSH-1075 | CH-207-IN-DS-075
357 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Flow Elements For Unit 200 | 4.8265 | 0.02194% | 17202B-200-IN-DSH-1076 | CH-207-IN-DS-076
358 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Flow Elements For Unit 200(Final Issue) | 26.7603 | 0.1216% | 17202B-200-IN-DSH-1076 | CH-207-IN-DS-076
359 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Flow Elements For Unit 300 | 4.68 | 0.02127% | 17202B-300-IN-DSH-1077 | CH-207-IN-DS-077
360 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Flow Elements For Unit 300(Final Issue) | 26.2495 | 0.1193% | 17202B-300-IN-DSH-1077 | CH-207-IN-DS-077
361 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Flow Elements For Unit 400 | 4.68 | 0.02127% | 17202B-400-IN-DSH-1078 | CH-207-IN-DS-078
362 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Flow Elements For Unit 400(Final Issue) | 26.2495 | 0.1193% | 17202B-400-IN-DSH-1078 | CH-207-IN-DS-078
363 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Flow Elements For Unit 500 | 4.68 | 0.02127% | 17202B-500-IN-DSH-1079 | CH-207-IN-DS-079
364 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Flow Elements For Unit 500(Final Issue) | 26.2495 | 0.1193% | 17202B-500-IN-DSH-1079 | CH-207-IN-DS-079
365 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Flow Elements For Unit 600 | 4.8265 | 0.02194% | 17202B-600-IN-DSH-1080 | CH-207-IN-DS-080
366 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Flow Elements For Unit 600(Final Issue) | 26.7603 | 0.1216% | 17202B-600-IN-DSH-1080 | CH-207-IN-DS-080
367 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Gauges For Unit 100 | 4.68 | 0.02127% | 17202B-100-IN-DSH-1081 | CH-207-IN-DS-081
368 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Gauges For Unit 100(Final Issue) | 26.2495 | 0.1193% | 17202B-100-IN-DSH-1081 | CH-207-IN-DS-081
369 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Gauges For Unit 200 | 4.8265 | 0.02194% | 17202B-200-IN-DSH-1082 | CH-207-IN-DS-082
370 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Gauges For Unit 200(Final Issue) | 26.7603 | 0.1216% | 17202B-200-IN-DSH-1082 | CH-207-IN-DS-082
371 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Gauges For Unit 300 | 4.68 | 0.02127% | 17202B-300-IN-DSH-1083 | CH-207-IN-DS-083
372 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Gauges For Unit 300(Final Issue) | 26.2495 | 0.1193% | 17202B-300-IN-DSH-1083 | CH-207-IN-DS-083
373 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Gauges For Unit 400 | 4.68 | 0.02127% | 17202B-400-IN-DSH-1084 | CH-207-IN-DS-084
374 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Gauges For Unit 400(Final Issue) | 26.2495 | 0.1193% | 17202B-400-IN-DSH-1084 | CH-207-IN-DS-084
375 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Gauges For Unit 500 | 4.68 | 0.02127% | 17202B-500-IN-DSH-1085 | CH-207-IN-DS-085
376 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Gauges For Unit 500(Final Issue) | 26.2495 | 0.1193% | 17202B-500-IN-DSH-1085 | CH-207-IN-DS-085
377 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Gauges For Unit 600 | 4.8265 | 0.02194% | 17202B-600-IN-DSH-1086 | CH-207-IN-DS-086
378 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Gauges For Unit 600(Final Issue) | 26.7603 | 0.1216% | 17202B-600-IN-DSH-1086 | CH-207-IN-DS-086
379 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Transmitters (Displacer Type) For Unit 100 | 4.68 | 0.02127% | 17202B-100-IN-DSH-1087 | CH-207-IN-DS-087
380 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Transmitters (Displacer Type) For Unit 100 (Final Issue) | 26.2495 | 0.1193% | 17202B-100-IN-DSH-1087 | CH-207-IN-DS-087
381 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Transmitters (Displacer Type) For Unit 200 | 4.8265 | 0.02194% | 17202B-200-IN-DSH-1088 | CH-207-IN-DS-088
382 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Transmitters (Displacer Type) For Unit 200 (Final Issue) | 26.7603 | 0.1216% | 17202B-200-IN-DSH-1088 | CH-207-IN-DS-088
383 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Transmitters (Displacer Type) For Unit 300 | 4.68 | 0.02127% | 17202B-300-IN-DSH-1089 | CH-207-IN-DS-089
384 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Transmitters (Displacer Type) For Unit 300 (Final Issue) | 26.2495 | 0.1193% | 17202B-300-IN-DSH-1089 | CH-207-IN-DS-089
385 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Transmitters (Displacer Type) For Unit 400 | 4.68 | 0.02127% | 17202B-400-IN-DSH-1090 | CH-207-IN-DS-090
386 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Transmitters (Displacer Type) For Unit 400 (Final Issue) | 26.2495 | 0.1193% | 17202B-400-IN-DSH-1090 | CH-207-IN-DS-090
387 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Transmitters (Displacer Type) For Unit 500 | 4.68 | 0.02127% | 17202B-500-IN-DSH-1091 | CH-207-IN-DS-091
388 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Transmitters (Displacer Type) For Unit 500 (Final Issue) | 26.2495 | 0.1193% | 17202B-500-IN-DSH-1091 | CH-207-IN-DS-091
389 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Transmitters (Displacer Type) For Unit 600 | 4.8265 | 0.02194% | 17202B-600-IN-DSH-1092 | CH-207-IN-DS-092
390 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Transmitters (Displacer Type) For Unit 600 (Final Issue) | 26.7603 | 0.1216% | 17202B-600-IN-DSH-1092 | CH-207-IN-DS-092
391 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Transmitters (Radar Type) For Unit 400 | 4.68 | 0.02127% | 17202B-400-IN-DSH-1093 | CH-207-IN-DS-093
392 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Level Transmitters (Radar Type) For Unit 400(Final Issue) | 26.2495 | 0.1193% | 17202B-400-IN-DSH-1093 | CH-207-IN-DS-093
393 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Pressure and Diff. Pressure Gauges For Unit 100 | 4.68 | 0.02127% | 17202B-100-IN-DSH-1094 | CH-207-IN-DS-094
394 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Pressure and Diff. Pressure Gauges For Unit 100(Final Issue) | 26.2495 | 0.1193% | 17202B-100-IN-DSH-1094 | CH-207-IN-DS-094
395 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Pressure and Diff. Pressure Gauges For Unit 200 | 4.8265 | 0.02194% | 17202B-200-IN-DSH-1095 | CH-207-IN-DS-095
396 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Pressure and Diff. Pressure Gauges For Unit 200(Final Issue) | 26.7603 | 0.1216% | 17202B-200-IN-DSH-1095 | CH-207-IN-DS-095
397 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Pressure and Diff. Pressure Gauges For Unit 300 | 4.68 | 0.02127% | 17202B-300-IN-DSH-1096 | CH-207-IN-DS-096
398 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Pressure and Diff. Pressure Gauges For Unit 300(Final Issue) | 26.2495 | 0.1193% | 17202B-300-IN-DSH-1096 | CH-207-IN-DS-096
399 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Pressure and Diff. Pressure Gauges For Unit 400 | 4.68 | 0.02127% | 17202B-400-IN-DSH-1097 | CH-207-IN-DS-097
400 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Pressure and Diff. Pressure Gauges For Unit 400(Final Issue) | 26.2495 | 0.1193% | 17202B-400-IN-DSH-1097 | CH-207-IN-DS-097
401 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Pressure and Diff. Pressure Gauges For Unit 500 | 4.68 | 0.02127% | 17202B-500-IN-DSH-1098 | CH-207-IN-DS-098
402 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Pressure and Diff. Pressure Gauges For Unit 500(Final Issue) | 26.2495 | 0.1193% | 17202B-500-IN-DSH-1098 | CH-207-IN-DS-098
403 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Pressure and Diff. Pressure Gauges For Unit 600 | 4.8265 | 0.02194% | 17202B-600-IN-DSH-1099 | CH-207-IN-DS-099
404 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Pressure and Diff. Pressure Gauges For Unit 600(Final Issue) | 26.7603 | 0.1216% | 17202B-600-IN-DSH-1099 | CH-207-IN-DS-099
405 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Pressure and Diff. Pressure Transmitters For Unit 100 | 4.68 | 0.02127% | 17202B-100-IN-DSH-1100 | CH-207-IN-DS-100
406 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Pressure and Diff. Pressure Transmitters For Unit 100(Final Issue) | 26.2495 | 0.1193% | 17202B-100-IN-DSH-1100 | CH-207-IN-DS-100
407 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Pressure and Diff. Pressure Transmitters For Unit 200 | 4.8265 | 0.02194% | 17202B-200-IN-DSH-1101 | CH-207-IN-DS-101
408 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Pressure and Diff. Pressure Transmitters For Unit 200(Final Issue) | 26.7603 | 0.1216% | 17202B-200-IN-DSH-1101 | CH-207-IN-DS-101
409 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Pressure and Diff. Pressure Transmitters For Unit 300 | 4.68 | 0.02127% | 17202B-300-IN-DSH-1102 | CH-207-IN-DS-102
410 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Pressure and Diff. Pressure Transmitters For Unit 300(Final Issue) | 26.2495 | 0.1193% | 17202B-300-IN-DSH-1102 | CH-207-IN-DS-102
411 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Pressure and Diff. Pressure Transmitters For Unit 400 | 4.68 | 0.02127% | 17202B-400-IN-DSH-1103 | CH-207-IN-DS-103
412 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Pressure and Diff. Pressure Transmitters For Unit 400(Final Issue) | 26.2495 | 0.1193% | 17202B-400-IN-DSH-1103 | CH-207-IN-DS-103
413 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Pressure and Diff. Pressure Transmitters For Unit 500 | 4.68 | 0.02127% | 17202B-500-IN-DSH-1104 | CH-207-IN-DS-104
414 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Pressure and Diff. Pressure Transmitters For Unit 500(Final Issue) | 26.2495 | 0.1193% | 17202B-500-IN-DSH-1104 | CH-207-IN-DS-104
415 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Pressure and Diff. Pressure Transmitters For Unit 600 | 4.8265 | 0.02194% | 17202B-600-IN-DSH-1105 | CH-207-IN-DS-105
416 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Pressure and Diff. Pressure Transmitters For Unit 600(Final Issue) | 26.7603 | 0.1216% | 17202B-600-IN-DSH-1105 | CH-207-IN-DS-105
417 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Temperature Gauges For Unit 100 | 4.68 | 0.02127% | 17202B-100-IN-DSH-1106 | CH-207-IN-DS-106
418 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Temperature Gauges For Unit 100(Final Issue) | 26.2495 | 0.1193% | 17202B-100-IN-DSH-1106 | CH-207-IN-DS-106
419 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Temperature Gauges For Unit 200 | 4.8265 | 0.02194% | 17202B-200-IN-DSH-1107 | CH-207-IN-DS-107
420 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Temperature Gauges For Unit 200(Final Issue) | 26.7603 | 0.1216% | 17202B-200-IN-DSH-1107 | CH-207-IN-DS-107
421 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Temperature Gauges For Unit 300 | 4.68 | 0.02127% | 17202B-300-IN-DSH-1108 | CH-207-IN-DS-108
422 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Temperature Gauges For Unit 300(Final Issue) | 26.2495 | 0.1193% | 17202B-300-IN-DSH-1108 | CH-207-IN-DS-108
423 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Temperature Gauges For Unit 400 | 4.68 | 0.02127% | 17202B-400-IN-DSH-1109 | CH-207-IN-DS-109
424 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Temperature Gauges For Unit 400(Final Issue) | 26.2495 | 0.1193% | 17202B-400-IN-DSH-1109 | CH-207-IN-DS-109
425 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Temperature Gauges For Unit 500 | 4.68 | 0.02127% | 17202B-500-IN-DSH-1110 | CH-207-IN-DS-110
426 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Temperature Gauges For Unit 500(Final Issue) | 26.2495 | 0.1193% | 17202B-500-IN-DSH-1110 | CH-207-IN-DS-110
427 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Temperature Gauges For Unit 600 | 4.8265 | 0.02194% | 17202B-600-IN-DSH-1111 | CH-207-IN-DS-111
428 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Temperature Gauges For Unit 600(Final Issue) | 26.7603 | 0.1216% | 17202B-600-IN-DSH-1111 | CH-207-IN-DS-111
429 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Temperature Transmitters For Unit 100 | 4.68 | 0.02127% | 17202B-100-IN-DSH-1112 | CH-207-IN-DS-112
430 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Temperature Transmitters For Unit 100(Final Issue) | 26.2495 | 0.1193% | 17202B-100-IN-DSH-1112 | CH-207-IN-DS-112
431 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Temperature Transmitters For Unit 200 | 4.8265 | 0.02194% | 17202B-200-IN-DSH-1113 | CH-207-IN-DS-113
432 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Temperature Transmitters For Unit 200(Final Issue) | 26.7603 | 0.1216% | 17202B-200-IN-DSH-1113 | CH-207-IN-DS-113
433 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Temperature Transmitters For Unit 300 | 4.68 | 0.02127% | 17202B-300-IN-DSH-1114 | CH-207-IN-DS-114
434 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Temperature Transmitters For Unit 300(Final Issue) | 26.2495 | 0.1193% | 17202B-300-IN-DSH-1114 | CH-207-IN-DS-114
435 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Temperature Transmitters For Unit 400 | 4.68 | 0.02127% | 17202B-400-IN-DSH-1115 | CH-207-IN-DS-115
436 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Temperature Transmitters For Unit 400(Final Issue) | 26.2495 | 0.1193% | 17202B-400-IN-DSH-1115 | CH-207-IN-DS-115
437 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Temperature Transmitters For Unit 500 | 4.68 | 0.02127% | 17202B-500-IN-DSH-1116 | CH-207-IN-DS-116
438 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Temperature Transmitters For Unit 500(Final Issue) | 26.2495 | 0.1193% | 17202B-500-IN-DSH-1116 | CH-207-IN-DS-116
439 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Temperature Transmitters For Unit 600 | 4.8265 | 0.02194% | 17202B-600-IN-DSH-1117 | CH-207-IN-DS-117
440 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Temperature Transmitters For Unit 600(Final Issue) | 26.7603 | 0.1216% | 17202B-600-IN-DSH-1117 | CH-207-IN-DS-117
441 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Analysers For Unit 200 | 4.8265 | 0.02194% | 17202B-200-IN-DSH-1118 | CH-207-IN-DS-118
442 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Analysers For Unit 200(Final Issue) | 26.7603 | 0.1216% | 17202B-200-IN-DSH-1118 | CH-207-IN-DS-118
443 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Analysers For Unit 300 | 4.68 | 0.02127% | 17202B-300-IN-DSH-1119 | CH-207-IN-DS-119
444 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Analysers For Unit 300(Final Issue) | 26.2495 | 0.1193% | 17202B-300-IN-DSH-1119 | CH-207-IN-DS-119
445 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Analysers For Unit 400 | 4.68 | 0.02127% | 17202B-400-IN-DSH-1120 | CH-207-IN-DS-120
446 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Analysers For Unit 400(Final Issue) | 26.2495 | 0.1193% | 17202B-400-IN-DSH-1120 | CH-207-IN-DS-120
447 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Corrosion Probes For Unit 100 | 4.68 | 0.02127% | 17202B-100-IN-DSH-1121 | CH-207-IN-DS-121
448 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Corrosion Probes For Unit 100(Final Issue) | 26.2495 | 0.1193% | 17202B-100-IN-DSH-1121 | CH-207-IN-DS-121
449 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Corrosion Probes For Unit 200 | 4.8265 | 0.02194% | 17202B-200-IN-DSH-1122 | CH-207-IN-DS-122
450 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Corrosion Probes For Unit 200(Final Issue) | 26.7603 | 0.1216% | 17202B-200-IN-DSH-1122 | CH-207-IN-DS-122
451 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Corrosion Probes For Unit 300 | 4.68 | 0.02127% | 17202B-300-IN-DSH-1123 | CH-207-IN-DS-123
452 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Corrosion Probes For Unit 300(Final Issue) | 26.2495 | 0.1193% | 17202B-300-IN-DSH-1123 | CH-207-IN-DS-123
453 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Corrosion Probes For Unit 400 | 4.68 | 0.02127% | 17202B-400-IN-DSH-1124 | CH-207-IN-DS-124
454 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Corrosion Probes For Unit 400(Final Issue) | 26.2495 | 0.1193% | 17202B-400-IN-DSH-1124 | CH-207-IN-DS-124
455 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Rotameters For Unit 100 | 4.68 | 0.02127% | 17202B-100-IN-DSH-1125 | CH-207-IN-DS-125
456 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Rotameters For Unit 100(Final Issue) | 26.2495 | 0.1193% | 17202B-100-IN-DSH-1125 | CH-207-IN-DS-125
457 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Rotameters For Unit 200 | 4.8265 | 0.02194% | 17202B-200-IN-DSH-1126 | CH-207-IN-DS-126
458 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Rotameters For Unit 200(Final Issue) | 26.7603 | 0.1216% | 17202B-200-IN-DSH-1126 | CH-207-IN-DS-126
459 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Rotameters For Unit 300 | 4.68 | 0.02127% | 17202B-300-IN-DSH-1127 | CH-207-IN-DS-127
460 | INSTRUMENT | MEASURMENT & CONTROL INSTRUMENT | Data Sheet For Rotameters For Unit 300(Final Issue) | 26.2495 | 0.1193% | 17202B-300-IN-DSH-1127 | CH-207-IN-DS-127
461 | INSTRUMENT | IN06-ERECTION DRAWING |  | 133.2601 | 0.6057%
462 | INSTRUMENT | ERECTION DRAWING | Instrument Specification For Cables | 28.9591 | 0.1316% | 17202B-000-IN-SPC-1027 | CH-207-IN-SP-027
463 | INSTRUMENT | ERECTION DRAWING | Instrument Main Cable Route | 16.6255 | 0.07557% | 17202B-000-IN-00-LYT-1028 | CH-207-IN-A0-028
464 | INSTRUMENT | ERECTION DRAWING | Control Room Layout & Arrangement Panel Drawing | 19.3061 | 0.08775% | 17202B-000-IN-01-LYT-1029 | CH-207-IN-A1-029
465 | INSTRUMENT | ERECTION DRAWING | Instrument Material Take Off | 14.04 | 0.06382% | 17202B-000-IN-MTO-1030 | CH-207-IN-DC-030
466 | INSTRUMENT | ERECTION DRAWING | Instrument Material Take Off(Final Issue) | 26.2495 | 0.1193% | 17202B-000-IN-MTO-1030 | CH-207-IN-DC-030
467 | INSTRUMENT | ERECTION DRAWING | Instrument Power Consumption Diagram | 14.04 | 0.06382% | 17202B-000-03-IN-DIG-1031 | CH-207-IN-A3-031
468 | INSTRUMENT | ERECTION DRAWING | Instrument Air Consumption List | 14.04 | 0.06382% | 17202B-000-IN-LST-1032 | CH-207-IN-DC-032
469 | ELECTRICAL |  |  | 1002.6659 | 4.558%
470 | ELECTRICAL | EL01-DESIGN BASIS |  | 19.4219 | 0.08828%
471 | ELECTRICAL | DESIGN BASIS | Electrical Design Criteria | 19.4219 | 0.08828% | 17202B-000-EL-DSB-1001 | CH-207-EL-DC-001
472 | ELECTRICAL | EL02-SPECIFICATION |  | 182.9595 | 0.8316%
473 | ELECTRICAL | SPECIFICATION | Specification For Power & Distribution Transformer | 14.04 | 0.06382% | 17202B-000-EL-SPC-1002 | CH-207-EL-SP-002
474 | ELECTRICAL | SPECIFICATION | Specification For Low Voltage Switchgear /MCC | 14.04 | 0.06382% | 17202B-000-EL-SPC-1004 | CH-207-EL-SP-004
475 | ELECTRICAL | SPECIFICATION | Specification For Battery Charger & Batteries | 14.04 | 0.06382% | 17202B-000-EL-SPC-1005 | CH-207-EL-SP-005
476 | ELECTRICAL | SPECIFICATION | Specification For AC UPS & Batteries | 14.04 | 0.06382% | 17202B-000-EL-SPC-1006 | CH-207-EL-SP-006
477 | ELECTRICAL | SPECIFICATION | Specification For Emergency Diesel Generator | 14.04 | 0.06382% | 17202B-000-EL-SPC-1007 | CH-207-EL-SP-007
478 | ELECTRICAL | SPECIFICATION | Specification For LV Motors | 14.04 | 0.06382% | 17202B-000-EL-SPC-1009 | CH-207-EL-SP-009
479 | ELECTRICAL | SPECIFICATION | Specification For Capacitor Bank | 14.04 | 0.06382% | 17202B-000-EL-SPC-1010 | CH-207-EL-SP-010
480 | ELECTRICAL | SPECIFICATION | Specification For Power & Control Cables | 14.04 | 0.06382% | 17202B-000-EL-SPC-1011 | CH-207-EL-SP-011
481 | ELECTRICAL | SPECIFICATION | Specification For Cathodic Protection System | 14.04 | 0.06382% | 17202B-000-EL-SPC-1012 | CH-207-EL-SP-012
482 | ELECTRICAL | SPECIFICATION | Specification For Electrical Bulk Materials | 14.04 | 0.06382% | 17202B-000-EL-SPC-1013 | CH-207-EL-SP-013
483 | ELECTRICAL | SPECIFICATION | Specification For Earthing And Lightning Protection System | 14.04 | 0.06382% | 17202B-000-EL-SPC-1042 | CH-207-EL-SP-042
484 | ELECTRICAL | SPECIFICATION | Specification For Lighting And Small Power System | 14.04 | 0.06382% | 17202B-000-EL-SPC-1043 | CH-207-EL-SP-043
485 | ELECTRICAL | SPECIFICATION | Specification For Heat Tracing System | 14.4795 | 0.06582% | 17202B-000-EL-SPC-1003 | CH-207-EL-SP-003
486 | ELECTRICAL | EL03-POWER DISTRIBUTION |  | 445.9679 | 2.027%
487 | ELECTRICAL | POWER DISTRIBUTION | UPS & Battery Charger Sizing Calculation Report | 48.491 | 0.2204% | 17202B-000-EL-CSH-1014 | CH-207-EL-DC-014
488 | ELECTRICAL | POWER DISTRIBUTION | Cable Sizing Calculation Report | 46.8 | 0.2127% | 17202B-000-EL-CSH-1044 | CH-207-EL-DC-044
489 | ELECTRICAL | POWER DISTRIBUTION | Power System Analysis Report (Load Flow, Short Circuit, Motor Starting) | 46.8 | 0.2127% | 17202B-000-EL-CSH-1045 | CH-207-EL-DC-045
490 | ELECTRICAL | POWER DISTRIBUTION | Electrical Load List | 48.0292 | 0.2183% | 17202B-000-EL-LOL-1015 | CH-207-EL-DC-015
491 | ELECTRICAL | POWER DISTRIBUTION | Power And Control Cable Schedule | 48.0292 | 0.2183% | 17202B-000-EL-SCH-1016 | CH-207-EL-DC-016
492 | ELECTRICAL | POWER DISTRIBUTION | Data Sheet For Power And Distribution Transformer | 18.4728 | 0.08397% | 17202B-000-EL-DSH-1017 | CH-207-EL-DS-017
493 | ELECTRICAL | POWER DISTRIBUTION | Data Sheet For LV Switchgear/MCC | 18.4728 | 0.08397% | 17202B-000-EL-DSH-1019 | CH-207-EL-DS-019
494 | ELECTRICAL | POWER DISTRIBUTION | Data Sheet For Battery Charger And Batteries | 18.4728 | 0.08397% | 17202B-000-EL-DSH-1020 | CH-207-EL-DS-020
495 | ELECTRICAL | POWER DISTRIBUTION | Data Sheet For UPS And Batteries | 18.4728 | 0.08397% | 17202B-000-EL-DSH-1021 | CH-207-EL-DS-021
496 | ELECTRICAL | POWER DISTRIBUTION | Data Sheet For Emergency Generator | 18.4728 | 0.08397% | 17202B-000-EL-DSH-1022 | CH-207-EL-DS-022
497 | ELECTRICAL | POWER DISTRIBUTION | LV Single Line Diagram/MCC | 55.4183 | 0.2519% | 17202B-000-01-EL-SLD-1024 | CH-207-EL-A1-024
498 | ELECTRICAL | POWER DISTRIBUTION | Main Cable Routing Layout | 24.9382 | 0.1134% | 17202B-000-00-EL-LYT-1025 | CH-207-EL-A0-025
499 | ELECTRICAL | POWER DISTRIBUTION | Substation Building Arrangement Layout | 24.9382 | 0.1134% | 17202B-900-01-EL-LYT-1026 | CH-207-EL-A1-026
500 | ELECTRICAL | POWER DISTRIBUTION | Power Installation Details | 10.16 | 0.04618% | 17202B-000-04-EL-SDG-1027 | CH-207-EL-A4-027
501 | ELECTRICAL | EL04-LIGHTING SYSTEM |  | 129.7711 | 0.5899%
502 | ELECTRICAL | LIGHTING SYSTEM | Lighting System Calculation Report | 30.0182 | 0.1364% | 17202B-000-EL-CSH-1029 | CH-207-EL-DC-029
503 | ELECTRICAL | LIGHTING SYSTEM | General Area Lighting Layout | 19.8582 | 0.09026% | 17202B-000-00-EL-LYT-1030 | CH-207-EL-A0-030
504 | ELECTRICAL | LIGHTING SYSTEM | Substation Building Lighting Layout | 19.8582 | 0.09026% | 17202B-900-01-EL-LYT-1031 | CH-207-EL-A1-031
505 | ELECTRICAL | LIGHTING SYSTEM | Restaurant Building Lighting Layout | 49.8765 | 0.2267% | 17202B-950-01-EL-LYT-1032 | CH-207-EL-A1-032
506 | ELECTRICAL | LIGHTING SYSTEM | Lighting System Installation Details | 10.16 | 0.04618% | 17202B-000-04-EL-SDG-1033 | CH-207-EL-A4-033
507 | ELECTRICAL | EL05-EARTHING SYSTEM |  | 99.7529 | 0.4534%
508 | ELECTRICAL | EARTHING SYSTEM | Grounding System Calculation Report | 30.0182 | 0.1364% | 17202B-000-EL-CSH-1034 | CH-207-EL-DC-034
509 | ELECTRICAL | EARTHING SYSTEM | Overall Earthing Layout | 19.8582 | 0.09026% | 17202B-000-00-EL-LYT-1035 | CH-207-EL-A0-035
510 | ELECTRICAL | EARTHING SYSTEM | Substation Building Earthing Layout | 19.8582 | 0.09026% | 17202B-900-01-EL-LYT-1036 | CH-207-EL-A1-036
511 | ELECTRICAL | EARTHING SYSTEM | Restaurant Building Earthing Layout | 19.8582 | 0.09026% | 17202B-950-01-EL-LYT-1037 | CH-207-EL-A1-037
512 | ELECTRICAL | EARTHING SYSTEM | Earthing System Installation Details | 10.16 | 0.04618% | 17202B-000-04-EL-SDG-1038 | CH-207-EL-A4-038
513 | ELECTRICAL | EL06-MATERIAL TAKE OFF |  | 74.8147 | 0.3401%
514 | ELECTRICAL | MATERIAL TAKE OFF | Electrical Material Take off | 74.8147 | 0.3401% | 17202B-000-EL-MTO-1028 | CH-207-EL-DC-028
515 | ELECTRICAL | EL07-CHATHODIC PROTECTION SYSTEM |  | 19.9597 | 0.09073%
516 | ELECTRICAL | CATHODIC PROTECTION SYSTEM | Cathodic Protection System Installation Details | 19.9597 | 0.09073% | 17202B-150-04-EL-SDG-1041 | CH-207-EL-A4-041
517 | ELECTRICAL | EL08-GENERAL DRAWING |  | 30.0182 | 0.1364%
518 | ELECTRICAL | GENERAL DRAWING | Electrical Hazardous Area Classification Drawing | 30.0182 | 0.1364% | 17202B-000-03-EL-DWG-1008 | CH-207-EL-A3-008
519 | TELECOM |  |  | 395.7789 | 1.799%
520 | TELECOM | TL01-DESIGN BASIS |  | 20.7819 | 0.09446%
521 | TELECOM | DESIGN BASIS | Telecom Design Criteria | 20.7819 | 0.09446% | 17202B-000-TL-DSB-1001 | CH-207-TM-DC-001
522 | TELECOM | TL02-SPECIFICATION |  | 27.7091 | 0.126%
523 | TELECOM | SPECIFICATION | Specification For Telephone System | 9.2364 | 0.04198% | 17202B-000-TL-SPC-1002 | CH-207-TM-SP-002
524 | TELECOM | SPECIFICATION | Specification For Paging System | 9.2364 | 0.04198% | 17202B-000-TL-SPC-1003 | CH-207-TM-SP-003
525 | TELECOM | SPECIFICATION | Specification For Closed Circuit TV System | 9.2364 | 0.04198% | 17202B-000-TL-SPC-1004 | CH-207-TM-SP-004
526 | TELECOM | TL03-DRAWING |  | 273.3968 | 1.243%
527 | TELECOM | DRAWING | Telephone System Block Diagram | 23.0909 | 0.105% | 17202B-000-01-TL-BKD-1005 | CH-207-TM-A1-005
528 | TELECOM | DRAWING | CCTV System Block Diagram | 23.0909 | 0.105% | 17202B-000-01-TL-BKD-1006 | CH-207-TM-A1-006
529 | TELECOM | DRAWING | Paging System Block Diagram | 23.0909 | 0.105% | 17202B-000-01-TL-BKD-1007 | CH-207-TM-A1-007
530 | TELECOM | DRAWING | Overall Closed Circuit TV System Layout | 27.7091 | 0.126% | 17202B-000-00-TL-LYT-1008 | CH-207-TM-A0-008
531 | TELECOM | DRAWING | Area Telephone Layout | 27.7091 | 0.126% | 17202B-000-01-TL-LYT-1009 | CH-207-TM-A1-009
532 | TELECOM | DRAWING | Area Paging Layout | 27.7091 | 0.126% | 17202B-000-01-TL-LYT-1010 | CH-207-TM-A1-010
533 | TELECOM | DRAWING | Substation Building Telephone Layout | 27.7091 | 0.126% | 17202B-900-01-TL-LYT-1011 | CH-207-TM-A1-011
534 | TELECOM | DRAWING | Substation Building Paging Layout | 27.7091 | 0.126% | 17202B-900-01-TL-LYT-1012 | CH-207-TM-A1-012
535 | TELECOM | DRAWING | Restaurant Building Telephone Layout | 27.7091 | 0.126% | 17202B-950-01-TL-LYT-1013 | CH-207-TM-A1-013
536 | TELECOM | DRAWING | Restaurant Building Paging Layout | 27.7091 | 0.126% | 17202B-950-01-TL-LYT-1014 | CH-207-TM-A1-014
537 | TELECOM | DRAWING | Telecom System Installation Details | 10.16 | 0.04618% | 17202B-000-04-TL-SDG-1015 | CH-207-TM-A4-015
538 | TELECOM | TL04-SCHEDULE AND LIST |  | 27.7091 | 0.126%
539 | TELECOM | SCHEDULE AND LIST | Telecom System Cable Schedule | 27.7091 | 0.126% | 17202B-000-01-TL-SCH-1016 | CH-207-TM-DC-016
540 | TELECOM | TL05-MATERIAL TAKE OFF |  | 46.1819 | 0.2099%
541 | TELECOM | MATERIAL TAKE OFF | Telecom System Material Take off | 46.1819 | 0.2099% | 17202B-000-01-TL-MTO-1017 | CH-207-TM-DC-017
542 | PIPING |  |  | 841.619 | 3.826%
543 | PIPING | PI01-DESIGN BASIS |  | 23.0909 | 0.105%
544 | PIPING | DESIGN BASIS | Piping Design Criteria | 23.0909 | 0.105% | 17202B-000-PI-DSB-1001 | CH-207-PI-DC-001
545 | PIPING | PI02-PIPING SPECIFICATION |  | 489.5281 | 2.225%
546 | PIPING | PIPING SPECIFICATION | Piping Material Specification (PMS) | 235.5277 | 1.071% | 17202B-000-PI-MSS-1002 | CH-207-PI-SP-002
547 | PIPING | PIPING SPECIFICATION | Specification For Fabrication | 23.0909 | 0.105% | 17202B-000-PI-SPC-1003 | CH-207-PI-SP-003
548 | PIPING | PIPING SPECIFICATION | Specification For Welding | 23.0909 | 0.105% | 17202B-000-PI-SPC-1004 | CH-207-PI-SP-004
549 | PIPING | PIPING SPECIFICATION | Specification For Insulation | 23.0909 | 0.105% | 17202B-000-PI-SPC-1005 | CH-207-PI-SP-005
550 | PIPING | PIPING SPECIFICATION | Specification For Paint | 23.0909 | 0.105% | 17202B-000-PI-SPC-1006 | CH-207-PI-SP-006
551 | PIPING | PIPING SPECIFICATION | Specification For Coating & Wrapping | 23.0909 | 0.105% | 17202B-000-PI-SPC-1007 | CH-207-PI-SP-007
552 | PIPING | PIPING SPECIFICATION | Specification of Stress Analysis | 23.0909 | 0.105% | 17202B-000-PI-SPC-1008 | CH-207-PI-SP-008
553 | PIPING | PIPING SPECIFICATION | Specification For Hydro Test | 23.0909 | 0.105% | 17202B-000-PI-SPC-1009 | CH-207-PI-SP-009
554 | PIPING | PIPING SPECIFICATION | Specification For Chemical Cleaning | 23.0909 | 0.105% | 17202B-000-PI-SPC-1010 | CH-207-PI-SP-010
555 | PIPING | PIPING SPECIFICATION | Specification For Pipe | 23.0909 | 0.105% | 17202B-000-PI-SPC-1022 | CH-207-PI-SP-022
556 | PIPING | PIPING SPECIFICATION | Specification For Flange and Fitting | 23.0909 | 0.105% | 17202B-000-PI-SPC-1023 | CH-207-PI-SP-023
557 | PIPING | PIPING SPECIFICATION | Specification For Manual Valve | 23.0909 | 0.105% | 17202B-000-PI-SPC-1024 | CH-207-PI-SP-024
558 | PIPING | PI03-PLOT PLAN |  | 211.7888 | 0.9627%
559 | PIPING | PLOT PLAN | General Plot Plan | 62.3456 | 0.2834% | 17202B-000-00-PI-PLN-1013 | CH-207-PI-A0-013
560 | PIPING | PLOT PLAN | Unit Plot Plan For Unit 100 | 21.349 | 0.09704% | 17202B-100-02-PI-PLN-1025 | CH-207-PI-A2-025
561 | PIPING | PLOT PLAN | Unit Plot Plan For Unit 200 | 21.349 | 0.09704% | 17202B-200-02-PI-PLN-1026 | CH-207-PI-A2-026
562 | PIPING | PLOT PLAN | Unit Plot Plan For Unit 300 | 21.349 | 0.09704% | 17202B-300-02-PI-PLN-1027 | CH-207-PI-A2-027
563 | PIPING | PLOT PLAN | Unit Plot Plan For Unit 400 | 21.349 | 0.09704% | 17202B-400-02-PI-PLN-1028 | CH-207-PI-A2-028
564 | PIPING | PLOT PLAN | Unit Plot Plan For Unit 500 | 21.349 | 0.09704% | 17202B-500-02-PI-PLN-1029 | CH-207-PI-A2-029
565 | PIPING | PLOT PLAN | Unit Plot Plan For Unit 600 | 21.349 | 0.09704% | 17202B-600-02-PI-PLN-1030 | CH-207-PI-A2-030
566 | PIPING | PLOT PLAN | Unit Plot Plan For Unit 900 | 21.349 | 0.09704% | 17202B-900-02-PI-PLN-1031 | CH-207-PI-A2-031
567 | PIPING | PI04-PIPING ERECTION DRAWING |  | 57.6364 | 0.262%
568 | PIPING | PIPING ERECTION DRAWING | Key Plan | 28.08 | 0.1276% | 17202B-000-00-PI-PLN-1015 | CH-207-PI-A0-015
569 | PIPING | PIPING ERECTION DRAWING | Piping Assembly Drawing | 29.5564 | 0.1343% | 17202B-000-04-PI-SDG-1016 | CH-207-PI-A4-016
570 | PIPING | PI05-PIPING MATERIAL |  | 29.5564 | 0.1343%
571 | PIPING | PIPING MATERIAL | Material Take Off For Piping | 29.5564 | 0.1343% | 17202B-000-PI-MTO-1017 | CH-207-PI-DC-017
572 | PIPING | PI06-STRESS ANALYSIS & SUPPORT |  | 30.0182 | 0.1364%
573 | PIPING | STRESS ANALYSIS & SUPPORT | Standard Pipe Support Drawing | 30.0182 | 0.1364% | 17202B-000-04-PI-SDG-1018 | CH-207-PI-A4-018
574 | EPC Package |  |  | 1100 | 5%
575 | GENERAL |  | EPC Package | 1100 | 5%